## 📊 Dashboard
🌍 60-DAY INTERNATIONAL AI/ML JOB SEARCH TRACKER
IIT Bombay M.Tech ¦ 5 Years MNC ¦ Dubai • UK • Germany • Netherlands • Ireland ¦ Starting: 10 May 2026
📋 APPLICATIONS |  |  |  | 📞 RECRUITER SCREENS |  |  |  | 🎯 INTERVIEWS
3 |  |  |  | 3 |  |  |  | 1
Target: 115 applications |  |  |  | Total outreach sent |  |  |  | Total interview rounds
3 |  |  |  | 2 |  |  |  | 0
Active in pipeline |  |  |  | Responses received |  |  |  | Rounds passed
0 |  |  |  | 0 |  |  |  | 0
Offers received |  |  |  | Calls scheduled |  |  |  | Offers from interviews
📈 WEEKLY PROGRESS SNAPSHOT
Week | Dates | Apps Sent | Recruiter Screens | Tech Rounds | Study Hours | LeetCode | Projects | LinkedIn Posts | Notes
Week 1 | May 10–16 | Target: 5 | 0 | 0 | 20h+ | 5 | 0 deployed | 1 | Foundation setup
Week 2 | May 17–23 | Target: 15 | 0–1 | 0 | 25h | 10 | Project 1 started | 1 | First outreach
Week 3 | May 24–30 | Target: 15 | 1–2 | 0–1 | 25h | 15 | Project 1 deployed | 1 | First recruiter call
Week 4 | May 31–Jun 6 | Target: 15 | 2–3 | 1–2 | 25h | 20 | Project 2 deployed | 1 | Fine-tuning + coding
Week 5 | Jun 7–13 | Target: 15 | 2–3 | 2–3 | 25h | 25 | Project 3 started | 1 | Tech interviews begin
Week 6 | Jun 14–20 | Target: 15 | 1–2 | 2–4 | 20h | 30 | Project 4 started | 1 | UAE offer possible
Week 7 | Jun 21–27 | Target: 15 | 1–2 | 2–4 | 20h | 35 | Project 5 started | 1 | Offer conversion
Week 8 | Jun 28–Jul 4 | Target: 10 | 1–2 | 2–4 | 15h | 40 | All 5 deployed | 0 | Negotiate offers
Week 9 | Jul 5–10 | Target: 10 | 1–2 | 1–3 | 10h | 45 | Complete | 0 | Accept best offer
🏆 KEY MILESTONES CHECKLIST
Milestone | Status | Date Completed
LinkedIn All-Star status achieved | ⬜ Not Started
Master resume v1.0 created & ATS-optimized | ⬜ Not Started
UAE resume v1.1 ready | ⬜ Not Started
UK resume v1.2 ready | ⬜ Not Started
GitHub cleaned — 3 projects pinned | ⬜ Not Started
20 UAE recruiters connected on LinkedIn | ⬜ Not Started
20 UK/Europe recruiters connected | ⬜ Not Started
First 5 applications submitted | ⬜ Not Started
Project 1 (Enterprise RAG) — DEPLOYED on GCP | ⬜ Not Started
Project 2 (Multi-Agent LangGraph) — DEPLOYED | ⬜ Not Started
Project 3 (AI Marketing Automation) — DEPLOYED | ⬜ Not Started
Project 4 (Full MLOps Stack) — DEPLOYED | ⬜ Not Started
Project 5 (Multi-Tenant SaaS) — DEPLOYED | ⬜ Not Started
First recruiter screen completed | ⬜ Not Started
First technical interview completed | ⬜ Not Started
First UAE offer received | ⬜ Not Started
First European offer received | ⬜ Not Started
Salary negotiated successfully | ⬜ Not Started
Visa sponsorship confirmed | ⬜ Not Started
Offer accepted — notice period started | ⬜ Not Started

## 📅 60-Day Planner
📅 60-DAY DAILY ACTIVITY PLANNER ¦ 10 May – 10 July 2026
Day | Date | Week | Priority | Morning Task (Study/Build) | Afternoon Task (Prep/Apply) | Evening Task (LeetCode/Outreach) | Study Hours | Apps Target | Status | Notes
1 | Sun 10 May | Week 1 | 🔴 CRITICAL | Update LinkedIn headline + About section + experience bullets | Create master resume v1.0 — ATS format, quantified bullets | GitHub audit: clean repos, write READMEs, pin 3 best projects | 9h | 0 | ⬜ Not Started
2 | Mon 11 May | Week 1 | 🔴 CRITICAL | Create accounts: LinkedIn Premium, Naukri Gulf, GulfTalent, Bayt, Wellfound | Set up Job Application Tracker (all 8 tabs from Section 9) | Research 50 target companies (20 UAE, 20 UK, 10 DE). Add to tracker | 7h | 0 | ⬜ Not Started
3 | Tue 12 May | Week 1 | 🟠 HIGH | Python: OOP — metaclasses, abstract classes, design patterns, decorators | Connect with 10 UAE recruiters on LinkedIn (use DM template) | SQL: Window functions — ROW_NUMBER, RANK, LAG, LEAD. LeetCode SQL x5 | 6h | 0 | ⬜ Not Started
4 | Wed 13 May | Week 1 | 🟠 HIGH | Statistics: CLT, hypothesis testing, p-values, confidence intervals | Create UAE-specific resume v1.1 (add nationality note, optimize for Gulf) | ML: Bias-variance, regularization (L1/L2), cross-validation | 6h | 0 | ⬜ Not Started
5 | Thu 14 May | Week 1 | 🟠 HIGH | GenAI: RAG architecture deep dive — chunking strategies, embedding models | Write LinkedIn post #1: '5 lessons from building production RAG systems' | LangChain/LangGraph: chains, agents, memory, tool calling. Read docs | 5h | 0 | ⬜ Not Started
6 | Fri 15 May | Week 1 | 🟠 HIGH | System Design: CAP theorem, microservices, API design, load balancing | ML System Design: feature stores, model serving patterns, A/B testing | Behavioral: Write 5 STAR stories (leadership, conflict, impact, failure) | 5h | 0 | ⬜ Not Started
7 | Sat 16 May | Week 1 | 🟡 MEDIUM | Deep Learning: backprop, CNN architectures, attention mechanism | Apply to FIRST 5 carefully selected UAE roles (tailored, not spray) | Vector Databases: Pinecone, Weaviate, Qdrant. Understand HNSW, ANN | 8h | 5 | ⬜ Not Started
8 | Sun 17 May | Week 2 | 🔴 CRITICAL | Project 1 START: Design Enterprise RAG architecture. Write README first | Project 1: Document parser (Docling/PyMuPDF), chunking, BGE embeddings | Apply 5 UK roles. Set up Qdrant locally | 9h | 5 | ⬜ Not Started
9 | Mon 18 May | Week 2 | 🔴 CRITICAL | Project 1: Retrieval layer (Qdrant), reranking (Cohere), generation chain | LLM Study: tokenization, BPE, attention math, transformer architecture | LLM: Fine-tuning methods — LoRA, QLoRA, PEFT deep dive | 9h | 5 | ⬜ Not Started
10 | Tue 19 May | Week 2 | 🟠 HIGH | FastAPI: async routes, dependency injection, JWT auth, background tasks | LangGraph: StateGraph, nodes, conditional edges, human-in-the-loop | Apply 3 Germany/Netherlands roles. Research EU Blue Card requirements | 6h | 3 | ⬜ Not Started
11 | Wed 20 May | Week 2 | 🟠 HIGH | Vector DB deep dive: HNSW index, product quantization, hybrid search | RAG Evaluation: RAGAS — faithfulness, context precision, answer relevancy | Project 1: Add RAGAS evaluation module. Push to GitHub | 6h | 0 | ⬜ Not Started
12 | Thu 21 May | Week 2 | 🟠 HIGH | Statistics: Bayesian inference, A/B testing sample size, MLE/MAP | LinkedIn post #2: 'Why RAG evaluation matters more than RAG retrieval' | Cold outreach: message 20 hiring managers at UAE/UK target companies | 6h | 0 | ⬜ Not Started
13 | Fri 22 May | Week 2 | 🟠 HIGH | ML: XGBoost, LightGBM, SHAP values, feature importance, Optuna | Behavioral prep: Add 5 STAR stories — 'no authority', ambiguous projects | Apply 5 Ireland/France roles | 6h | 2 | ⬜ Not Started
14 | Sat 23 May | Week 2 | 🟡 MEDIUM | Self mock interview (record): 5 tech questions + 3 behavioral | ML System Design: Design 'Recommendation system for e-commerce' end-to-end | Week review: analyze tracker, update resume if needed, plan week 3 | 6h | 0 | ⬜ Not Started
15 | Sun 24 May | Week 3 | 🔴 CRITICAL | Project 1 FINALIZE: FastAPI backend + Streamlit frontend + Docker | Project 1 DEPLOY to GCP Cloud Run. Update resume with deployment bullet | Apply 5 roles + follow-up on all Week 1–2 applications | 8h | 5 | ⬜ Not Started
16 | Mon 25 May | Week 3 | 🔴 CRITICAL | Project 2 START: Multi-Agent System — design LangGraph orchestrator + 3 sub-agents | Deep Learning: Transformers detail — multi-head attention, positional encoding | NLP: NER, semantic similarity, sentence embeddings (SBERT) | 8h | 5 | ⬜ Not Started
17 | Tue 26 May | Week 3 | 🟠 HIGH | GCP deep dive: Cloud Run, Vertex AI Pipelines, BigQuery ML, Pub/Sub | MLOps: MLflow experiment tracking, model registry, CI/CD for ML | Apply 3 more roles. Research salary ranges for your level in each country | 5h | 3 | ⬜ Not Started
18 | Wed 27 May | Week 3 | 🟠 HIGH | LeetCode INTENSIVE: Sliding Window x5, Hash Maps x5 | ML from scratch (numpy): logistic regression, gradient descent, backprop | LinkedIn post #3: 'My architecture for building multi-agent AI systems' | 5h | 0 | ⬜ Not Started
19 | Thu 28 May | Week 3 | 🔴 CRITICAL | Recruiter call script: elevator pitch (60 sec), visa discussion, salary prep | Docker: Dockerfile, docker-compose, multi-stage builds, networking | Research each target company: products, recent AI news, tech stack | 6h | 2 | ⬜ Not Started
20 | Fri 29 May | Week 3 | 🟠 HIGH | ML System Design: 'Real-time fraud detection' — features → serving → monitoring | System Design: scalable REST API with caching, rate limiting, auth | Apply 3 more roles | 5h | 3 | ⬜ Not Started
21 | Sat 30 May | Week 3 | 🟡 MEDIUM | Mock technical interview #2 (Pramp/Interviewing.io): ML + 1 coding problem | Week 3 review: response rate analysis, update resume if needed | Project 2: Build orchestrator with LangGraph. Tool definitions for sub-agents | 7h | 0 | ⬜ Not Started
22 | Sun 31 May | Week 4 | 🔴 CRITICAL | LLM Fine-tuning hands-on: QLoRA with Llama/Mistral on Google Colab | Project 2: Add web search + paper reader + fact checker agents | Apply 5 roles across all target countries + LinkedIn outreach | 8h | 5 | ⬜ Not Started
23 | Mon 01 Jun | Week 4 | 🔴 CRITICAL | Project 2 COMPLETE: FastAPI streaming backend + Streamlit frontend | Project 2 DEPLOY to GCP Cloud Run. Push to GitHub. Update resume | LLM Study: DPO vs RLHF, reward modeling, preference data | 7h | 5 | ⬜ Not Started
24 | Tue 02 Jun | Week 4 | 🟠 HIGH | Embeddings: word2vec, GloVe, BERT, contrastive learning, matryoshka | Prompt engineering: structured outputs, function calling, ReAct pattern | Apply 3 roles + follow-up all previous applications | 5h | 3 | ⬜ Not Started
25 | Wed 03 Jun | Week 4 | 🟠 HIGH | AI evaluation: BLEU, ROUGE, LLM-as-judge, human eval frameworks | Kubernetes basics: pods, deployments, services, ingress, HPA | LinkedIn post #4: 'How I built a 6-agent research system with LangGraph' | 5h | 0 | ⬜ Not Started
26 | Thu 04 Jun | Week 4 | 🟠 HIGH | Distributed systems: consistency models, sharding, message queues (Kafka) | Model monitoring: data drift, concept drift, Evidently AI, PromptLayer | Apply 3 roles. Target IIT Bombay alumni at companies for referrals | 5h | 3 | ⬜ Not Started
27 | Fri 05 Jun | Week 4 | 🟠 HIGH | AI security: prompt injection defenses, adversarial examples, guardrails | Salary negotiation deep prep: anchoring, competing offers, relocation ask | Behavioral: 5 more STAR stories — scale, cross-functional, vision | 5h | 2 | ⬜ Not Started
28 | Sat 06 Jun | Week 4 | 🟡 MEDIUM | Full mock interview #3 (all rounds): HR + tech + system design + behavioral | Project 3 START: AI Marketing Automation — design architecture | Week 4 review + update all trackers | 7h | 0 | ⬜ Not Started
29 | Sun 07 Jun | Week 5 | 🔴 CRITICAL | Project 3: Customer segmentation (K-means + RFM), CTR prediction (XGBoost) | Project 3: Content generation pipeline with Vertex AI prompt templates | Apply 5 roles + deep company research for upcoming interviews | 8h | 5 | ⬜ Not Started
30 | Mon 08 Jun | Week 5 | 🔴 CRITICAL | Project 3 COMPLETE: MLflow tracking + FastAPI + Cloud Scheduler deploy | Project 3 DEPLOY to GCP. Update resume. Push GitHub | LLM: context window management, positional encoding types (RoPE, ALiBi) | 7h | 5 | ⬜ Not Started
31 | Tue 09 Jun | Week 5 | 🔴 CRITICAL | Inference optimization: KV cache, speculative decoding, vLLM, quantization | Prep for scheduled tech interview (company-specific research) | Apply 3 roles | 5h | 3 | ⬜ Not Started
32 | Wed 10 Jun | Week 5 | 🟠 HIGH | ML System Design: 'LLM-powered customer support system' end-to-end | LeetCode: Binary Search x5, Two Pointers x5 | Follow up on all Week 3+ applications | 5h | 0 | ⬜ Not Started
33 | Thu 11 Jun | Week 5 | 🟠 HIGH | Data Engineering basics: dbt, Airflow DAGs, data modeling, star schema | Case study prep: 'Design RAG for enterprise with 1M documents' | LinkedIn post #5: 'Production RAG lessons — what actually matters' | 5h | 3 | ⬜ Not Started
34 | Fri 12 Jun | Week 5 | 🟠 HIGH | Multi-agent advanced patterns: debate, critique, nested graphs | Mock technical deep dive: LLM Q&A + agentic system design (60 min solo) | Apply 3 roles + recruiter follow-up messages | 5h | 2 | ⬜ Not Started
35 | Sat 13 Jun | Week 5 | 🟡 MEDIUM | Full mock panel interview #4 (friend/mentor): simulate 3-interview day | Project 4 START: Production MLOps System — Feast + MLflow + Evidently design | Week 5 review + metrics | 7h | 0 | ⬜ Not Started
36 | Sun 14 Jun | Week 6 | 🔴 CRITICAL | Project 4: Feast feature store setup, XGBoost training pipeline, MLflow | Project 4: BentoML serving + Evidently drift detection + Cloud Run deploy | Apply 5 roles. Personalized cold emails to CTOs/AI leads at target startups | 8h | 5 | ⬜ Not Started
37 | Mon 15 Jun | Week 6 | 🔴 CRITICAL | Project 4 COMPLETE + DEPLOY. Update resume. Write architecture blog post | LLM: multimodal models, document AI, vision-language models overview | Apply 5 roles | 7h | 5 | ⬜ Not Started
38 | Tue 16 Jun | Week 6 | 🟠 HIGH | Coding: Graph algorithms x5 — BFS, DFS, shortest path (Dijkstra) | Company deep research for any interviews scheduled this week | Apply 3 roles | 5h | 3 | ⬜ Not Started
39 | Wed 17 Jun | Week 6 | 🟠 HIGH | Coding: Dynamic Programming x5 — knapsack, LCS, coin change | ML System Design: 'Feature store for 100M users real-time' | Follow up all applications older than 14 days | 5h | 0 | ⬜ Not Started
40 | Thu 18 Jun | Week 6 | 🟠 HIGH | Mock full-day interview simulation: 4 rounds back-to-back (4 hours) | Resume v3.0: incorporate all new project bullets, refresh metrics | LinkedIn post #6: 'MLOps stack for production AI systems' | 7h | 3 | ⬜ Not Started
41 | Fri 19 Jun | Week 6 | 🟠 HIGH | Data structures review: trees, heaps, tries — implement from scratch | Offer evaluation framework: salary + equity + visa + relocation + growth | Apply 3 roles | 5h | 2 | ⬜ Not Started
42 | Sat 20 Jun | Week 6 | 🟡 MEDIUM | Week 6 review + rest day (no heavy studying) | Project 5 START: Multi-Tenant SaaS — design data isolation architecture | Catch up on applications + follow-ups | 4h | 0 | ⬜ Not Started
43 | Sun 21 Jun | Week 7 | 🔴 CRITICAL | Project 5: Confluence/GDrive connectors, chunking, Qdrant multi-collection | Project 5: JWT + RBAC auth, FastAPI middleware, PostgreSQL tenant config | Apply 5 roles + IIT Bombay alumni network outreach (10 messages) | 8h | 5 | ⬜ Not Started
44 | Mon 22 Jun | Week 7 | 🔴 CRITICAL | Project 5 COMPLETE + DEPLOY. Update resume — 5 projects all live | Revision: all 5 projects' architectures — explain each in 5 minutes | Apply 5 roles | 7h | 5 | ⬜ Not Started
45 | Tue 23 Jun | Week 7 | 🔴 CRITICAL | Deep prep for scheduled interviews this week (company-specific) | LLM safety: constitutional AI, RLHF alignment, hallucination techniques | Apply 3 roles | 5h | 3 | ⬜ Not Started
46 | Wed 24 Jun | Week 7 | 🟠 HIGH | Revision marathon: LLM architecture → RAG → Agents → MLOps (1h each) | Practice system design out loud (record yourself): 2 designs | Apply 3 roles + follow-ups | 5h | 3 | ⬜ Not Started
47 | Thu 25 Jun | Week 7 | 🟠 HIGH | Salary negotiation role-play with friend or record yourself | Research relocation costs, neighborhoods, cost of living for top target cities | LinkedIn post #7: showcase all 5 projects in one post | 5h | 2 | ⬜ Not Started
48 | Fri 26 Jun | Week 7 | 🟠 HIGH | Final mock interview #5 — complete interview loop simulation | Prepare questions to ask interviewers (5 smart questions per company) | Apply 3 roles | 5h | 2 | ⬜ Not Started
49 | Sat 27 Jun | Week 7 | 🟡 MEDIUM | Week 7 review — assess pipeline, double down on highest-activity channels | Evaluate any offers received. Research counter-offer negotiation tactics | Catch-up on applications | 4h | 0 | ⬜ Not Started
50 | Sun 28 Jun | Week 8 | 🔴 CRITICAL | Offer management: compare offers in detail (salary, equity, visa, culture) | Negotiate salary: email/call script prep for each pending offer | Apply 5 roles to maintain pipeline pressure | 6h | 5 | ⬜ Not Started
51 | Mon 29 Jun | Week 8 | 🔴 CRITICAL | If no offer yet: audit resume + LinkedIn. Get reviewed by 2 more people | Expand: add Canada (Toronto), Singapore, Australia to application pipeline | Apply 5 roles — also try contract/freelance AI roles | 6h | 5 | ⬜ Not Started
52 | Tue 30 Jun | Week 8 | 🟠 HIGH | Deep prep for any live interviews in pipeline this week | Practice visa discussion: frame positively, know exact process | Apply 3 roles | 5h | 3 | ⬜ Not Started
53 | Wed 01 Jul | Week 8 | 🟠 HIGH | Review: ML fundamentals rapid-fire Q&A (self-test 30 questions) | Update LinkedIn about section to reflect all 5 deployed projects | Apply 3 roles + follow-up | 5h | 3 | ⬜ Not Started
54 | Thu 02 Jul | Week 8 | 🟠 HIGH | System design: practice 2 new questions from the top-10 list | Revision: statistics and probability rapid fire (20 questions) | LinkedIn post #8: project demo or technical insight | 5h | 2 | ⬜ Not Started
55 | Fri 03 Jul | Week 8 | 🟠 HIGH | Behavioral FINAL PREP: all 10 STAR stories polished and timed | Research immigration consultants/lawyers for chosen target country | Apply 3 roles | 5h | 2 | ⬜ Not Started
56 | Sat 04 Jul | Week 8 | 🟡 MEDIUM | Week 8 review. Calculate pipeline statistics. Identify conversion weak spots | Rest + recovery. Light reading only. | Update all trackers with current status | 3h | 0 | ⬜ Not Started
57 | Sun 05 Jul | Week 9 | 🔴 CRITICAL | Active interview follow-ups. Thank you notes within 24h of each round | If multiple offers: create comparison matrix (total comp, visa, growth) | Apply 5 roles — keep volume up | 6h | 5 | ⬜ Not Started
58 | Mon 06 Jul | Week 9 | 🔴 CRITICAL | Negotiate final offer: salary + equity + relocation + signing bonus | Research target country's tax system, banking, housing | Apply 5 roles | 6h | 5 | ⬜ Not Started
59 | Tue 07 Jul | Week 9 | 🟠 HIGH | Final round prep for any companies still in process | Visa application checklist: gather all documents needed | Apply 3 roles | 5h | 3 | ⬜ Not Started
60 | Wed 08 Jul | Week 9 | 🔴 CRITICAL | FINAL DAY: Review 60-day journey. Accept best offer. Plan notice period. | Write LinkedIn post announcing move (after acceptance) | Celebrate 🎉 — you did it | 2h | 0 | ⬜ Not Started

## 📋 Applications
📋 JOB APPLICATION TRACKER ¦ Target: 115+ Applications in 60 Days
# | Date Applied | Company | Role Title | Status | Location | Country | Platform | Resume Version | JD URL | Recruiter | Follow-up Date | Priority | Salary Range | Notes
1 | 10/05/2026 | Example: G42 | Senior AI Engineer | Applied | Abu Dhabi | UAE/Dubai | LinkedIn | v1.1-UAE | https://g42.ai/careers | Jane Smith | 24/05/2026 | 🔴 High | AED 40–50K/mo | Strong fit — GenAI focus
2 | 12/05/2026 | Example: DeepMind | Research Engineer (LLM) | Applied | London | UK | Direct (Website) | v1.2-UK | https://deepmind.com/careers |  | 26/05/2026 | 🔴 High | £90–110K/yr | Apply to team page directly
3 | 14/05/2026 | Example: Booking.com | ML Engineer | Applied | Amsterdam | Netherlands | LinkedIn | v1.3-NL | https://jobs.booking.com |  | 28/05/2026 | 🟡 Medium | €85–100K/yr | 30% ruling applies

## 📞 Outreach
📞 RECRUITER & HIRING MANAGER OUTREACH TRACKER ¦ Target: 100+ Contacts
# | Date | Name | Title | Company | Country | Msg Sent? | Response? | Outcome | Follow-up #1 | Follow-up #2 | LinkedIn URL | Notes
1 | 10/05/2026 | Example: Sarah Al-Rashid | Technical Recruiter | G42 | UAE/Dubai | Yes | Not Yet | Pending | 24/05/2026 | 07/06/2026 | linkedin.com/in/... | Sent DM template on Day 3
2 | 10/05/2026 | Example: Tom Richards | Talent Acquisition | DeepMind | UK | Yes | Not Yet | Pending | 24/05/2026 | 07/06/2026 | linkedin.com/in/... | Connected after applying

## 🎯 Interviews
🎯 INTERVIEW TRACKER ¦ Goal: 10–21 Rounds ¦ 1–3 Offers by Day 60
# | Company | Role | Country | Round # | Type | Date & Time | Interviewer | Format | Status | Salary Discussed | Outcome / Next Steps | Questions Asked | My Notes

## 🚀 Projects
🚀 PROJECT TRACKER ¦ 5 Production AI Projects ¦ Target: All Deployed by Day 50
Project | Title | Target Role | Tech Stack | Time Estimate | Start Day | Deploy Day | GitHub URL
Project 1 | Enterprise RAG Platform with Evaluation | GenAI/LLM Engineer | Qdrant + BGE-large + RAGAS + FastAPI + GCP | 2 weekends (16–20h) | Day 8 | Day 15 | https://github.com/yourusername/enterprise-rag
Project 2 | Multi-Agent Research & Report Generation | AI Agent / LLM Engineer | LangGraph + Tavily + PostgreSQL checkpointer + FastAPI | 3 weekends (20–25h) | Day 15 | Day 23 | https://github.com/yourusername/multi-agent-research
Project 3 | AI Marketing Campaign Automation | Data Scientist / ML Engineer | XGBoost + Vertex AI + MLflow + Cloud Scheduler | 2 weekends (14–18h) | Day 22 | Day 30 | https://github.com/yourusername/ai-marketing
Project 4 | Production ML System with Full MLOps Stack | ML Engineer / MLOps | Feast + MLflow + BentoML + Evidently + Terraform + CI/CD | 3 weekends (20–25h) | Day 29 | Day 37 | https://github.com/yourusername/mlops-stack
Project 5 | Multi-Tenant AI Knowledge Assistant (SaaS) | Senior AI/GenAI Engineer | Qdrant multi-collection + FastAPI + PostgreSQL + Redis + JWT/RBAC | 4 weekends (28–35h) | Day 36 | Day 44 | https://github.com/yourusername/ai-knowledge-saas
📋 PROJECT TASK BREAKDOWN — Check off each task as you complete it
Project | Task | Details | Est. Hours | Status | Date Done | Notes
Project 1 | Design architecture | Draw full system diagram. Write README first. | 2h | ⬜ Not Started
Project 1 | Document ingestion | PDF/DOCX parsing with Docling, cleaning pipeline | 3h | ⬜ Not Started
Project 1 | Chunking strategy | Implement fixed + semantic chunking, test chunk sizes | 2h | ⬜ Not Started
Project 1 | Embedding pipeline | BGE-large-en-v1.5 via HuggingFace, batch embedding | 2h | ⬜ Not Started
Project 1 | Qdrant vector store | Local setup, collection creation, hybrid search | 2h | ⬜ Not Started
Project 1 | Reranking layer | Cohere Rerank v3 integration + threshold tuning | 1h | ⬜ Not Started
Project 1 | RAGAS evaluation | Set up 4 metrics: faithfulness, recall, precision, relevancy | 2h | ⬜ Not Started
Project 1 | FastAPI backend | POST /query endpoint, streaming, error handling, auth | 3h | ⬜ Not Started
Project 1 | Streamlit frontend | Upload UI, query box, answer display, source citations | 2h | ⬜ Not Started
Project 1 | Docker + GCP deploy | Dockerfile, Cloud Run deploy, env vars, domain | 2h | ⬜ Not Started
Project 2 | LangGraph architecture | Design StateGraph: 6 nodes, routing logic, checkpointer | 3h | ⬜ Not Started
Project 2 | Orchestrator agent | Supervisor node: task decomposition, routing to sub-agents | 3h | ⬜ Not Started
Project 2 | Web search agent | Tavily API integration, results formatting, dedup | 2h | ⬜ Not Started
Project 2 | Paper reader agent | arXiv API + abstract extraction + citation parsing | 2h | ⬜ Not Started
Project 2 | Fact checker agent | Cross-reference claims across sources | 2h | ⬜ Not Started
Project 2 | Synthesis + writer agents | Combine findings, generate structured report | 2h | ⬜ Not Started
Project 2 | Human-in-the-loop | LangGraph interrupt for critical fact verification | 2h | ⬜ Not Started
Project 2 | FastAPI streaming | WebSocket endpoint for real-time agent progress | 2h | ⬜ Not Started
Project 2 | Deploy to GCP | Cloud Run + PostgreSQL checkpointer setup | 2h | ⬜ Not Started
Project 3 | Data pipeline | Customer CSV → segmentation features via Pandas + BigQuery | 2h | ⬜ Not Started
Project 3 | K-means segmentation | RFM feature engineering, cluster analysis, persona naming via LLM | 3h | ⬜ Not Started
Project 3 | CTR prediction model | XGBoost model, 0.78 AUC target, SHAP explainability | 3h | ⬜ Not Started
Project 3 | Content generation | Vertex AI prompt templates per segment, A/B variants | 2h | ⬜ Not Started
Project 3 | MLflow tracking | Log experiments, register model, artifact versioning | 2h | ⬜ Not Started
Project 3 | FastAPI + Celery | Async task queue for batch generation, status endpoint | 2h | ⬜ Not Started
Project 3 | Deploy + scheduler | Cloud Run deploy + Cloud Scheduler for weekly retraining | 2h | ⬜ Not Started
Project 4 | Feast feature store | Define feature views, online + offline store, materialization | 3h | ⬜ Not Started
Project 4 | Training pipeline | Vertex AI Pipelines (Kubeflow): data → train → validate → register | 4h | ⬜ Not Started
Project 4 | MLflow registry | Model versioning, staging → production promotion workflow | 2h | ⬜ Not Started
Project 4 | BentoML serving | Bentofile, Bento build, <50ms P95 latency target | 2h | ⬜ Not Started
Project 4 | Evidently monitoring | Data drift (PSI), prediction drift, auto-report generation | 2h | ⬜ Not Started
Project 4 | CI/CD pipeline | GitHub Actions: test → validate → deploy on main branch push | 3h | ⬜ Not Started
Project 4 | Terraform infra | GCP Cloud Run, Cloud SQL, GCS, IAM as code | 2h | ⬜ Not Started
Project 5 | Multi-tenant architecture | Qdrant collection per tenant, isolation design | 2h | ⬜ Not Started
Project 5 | Confluence connector | REST API pagination, incremental sync with delta tracking | 3h | ⬜ Not Started
Project 5 | Google Drive connector | Drive API, file type handling, change detection | 3h | ⬜ Not Started
Project 5 | Slack connector | Slack API, message history, channel filtering | 2h | ⬜ Not Started
Project 5 | JWT + RBAC auth | User roles, document-level permissions, middleware | 3h | ⬜ Not Started
Project 5 | Redis caching | Query result cache, TTL strategy, invalidation | 1h | ⬜ Not Started
Project 5 | Feedback loop | Thumbs up/down on answers, store feedback, RLHF data | 2h | ⬜ Not Started
Project 5 | Usage analytics | Query logs, popular topics, user engagement dashboard | 2h | ⬜ Not Started
Project 5 | Full GCP deploy | Cloud Run + Cloud SQL + GCS + Redis (Memorystore) | 3h | ⬜ Not Started

## 📚 Study Plan
📚 TECHNICAL STUDY TRACKER ¦ All Topics to Master for International AI/ML Interviews
Category | Topic | Importance | Interview Freq | Study Hours | Status | Date Completed | Key Resources / Notes
Python | OOP — classes, inheritance, magic methods, metaclasses | ⭐⭐⭐⭐⭐ | Every interview | 4h | ⬜ Not Started |  | Fluent Python Ch1-11
Python | Generators, decorators, context managers, closures | ⭐⭐⭐⭐⭐ | Every interview | 3h | ⬜ Not Started |  | Real Python advanced tutorials
Python | Async/await, threading vs multiprocessing, GIL | ⭐⭐⭐⭐ | Very High | 3h | ⬜ Not Started |  | David Beazley concurrency talk
Python | Type hints, Pydantic, testing (pytest, mocking) | ⭐⭐⭐⭐ | High | 2h | ⬜ Not Started |  | Pydantic docs + pytest docs
Python | Memory management, profiling, optimization | ⭐⭐⭐ | Medium | 2h | ⬜ Not Started |  | Python memory profiler docs
SQL | Window functions: ROW_NUMBER, RANK, LAG, LEAD, NTILE | ⭐⭐⭐⭐⭐ | 80% of DS roles | 3h | ⬜ Not Started |  | Mode Analytics SQL Tutorial
SQL | CTEs, recursive CTEs, complex subqueries | ⭐⭐⭐⭐⭐ | High | 3h | ⬜ Not Started |  | LeetCode SQL top 50
SQL | Query optimization: EXPLAIN, indexes, execution plans | ⭐⭐⭐⭐ | Medium | 3h | ⬜ Not Started |  | Use the Index, Luke (book)
SQL | Transactions, ACID, isolation levels | ⭐⭐⭐ | Medium | 2h | ⬜ Not Started |  | PostgreSQL docs
Statistics | Probability distributions, CLT, sampling | ⭐⭐⭐⭐⭐ | 90% of DS roles | 4h | ⬜ Not Started |  | StatQuest YouTube channel
Statistics | Hypothesis testing, t-test, chi-square, ANOVA | ⭐⭐⭐⭐⭐ | Very High | 4h | ⬜ Not Started |  | Khan Academy Stats
Statistics | A/B testing: sample size, p-values, multiple testing | ⭐⭐⭐⭐⭐ | Every DS role | 4h | ⬜ Not Started |  | Evan Miller's A/B testing guide
Statistics | Bayesian inference, MCMC, prior/posterior | ⭐⭐⭐⭐ | High | 4h | ⬜ Not Started |  | 3Blue1Brown Bayes video
Statistics | Causal inference: DiD, RCT, observational studies | ⭐⭐⭐ | Medium | 3h | ⬜ Not Started |  | 'The Effect' book (free online)
Machine Learning | Linear/Logistic Regression from scratch (numpy) | ⭐⭐⭐⭐⭐ | Every ML interview | 4h | ⬜ Not Started |  | Implement yourself — no library
Machine Learning | Tree methods: XGBoost, LightGBM, Random Forest | ⭐⭐⭐⭐⭐ | Very High | 5h | ⬜ Not Started |  | XGBoost paper + docs
Machine Learning | SHAP values, model explainability, fairness | ⭐⭐⭐⭐⭐ | High | 3h | ⬜ Not Started |  | SHAP library docs + Lundberg paper
Machine Learning | Class imbalance: SMOTE, threshold tuning, weighted loss | ⭐⭐⭐⭐ | High | 2h | ⬜ Not Started |  | imbalanced-learn docs
Machine Learning | Clustering: K-means, DBSCAN, GMM, hierarchical | ⭐⭐⭐ | Medium | 3h | ⬜ Not Started |  | Scikit-learn user guide
Deep Learning | Transformer architecture: attention, MHA, layer norm | ⭐⭐⭐⭐⭐ | All GenAI roles | 6h | ⬜ Not Started |  | Karpathy 'Let's build GPT' YouTube
Deep Learning | Backpropagation from scratch | ⭐⭐⭐⭐⭐ | Very High | 3h | ⬜ Not Started |  | Karpathy 'micrograd' YouTube
Deep Learning | CNN architectures: ResNet, EfficientNet, ViT | ⭐⭐⭐ | Medium | 3h | ⬜ Not Started |  | Papers with Code
Deep Learning | PyTorch: custom Dataset, DataLoader, training loop | ⭐⭐⭐⭐ | High | 4h | ⬜ Not Started |  | PyTorch official tutorials
LLMs | Pre-training: GPT (causal LM) vs BERT (masked LM) | ⭐⭐⭐⭐⭐ | Every LLM role | 4h | ⬜ Not Started |  | Karpathy lectures
LLMs | RLHF, DPO, reward modeling, preference datasets | ⭐⭐⭐⭐⭐ | Very High | 5h | ⬜ Not Started |  | Anthropic / DeepMind RLHF papers
LLMs | LoRA, QLoRA, PEFT, adapter methods — math + practice | ⭐⭐⭐⭐⭐ | Very High | 5h | ⬜ Not Started |  | HuggingFace PEFT docs + Raschka book
LLMs | Inference optimization: KV cache, vLLM, quantization | ⭐⭐⭐⭐ | High | 4h | ⬜ Not Started |  | vLLM docs + FlashAttention paper
LLMs | Prompt engineering: CoT, ReAct, structured outputs | ⭐⭐⭐⭐⭐ | Every GenAI role | 3h | ⬜ Not Started |  | Anthropic / OpenAI prompt guides
RAG Systems | Chunking strategies: fixed, semantic, late, parent-doc | ⭐⭐⭐⭐⭐ | 95% of GenAI roles | 3h | ⬜ Not Started |  | LangChain RAG docs
RAG Systems | Embedding models: dense, sparse, hybrid, late interaction | ⭐⭐⭐⭐⭐ | Very High | 3h | ⬜ Not Started |  | MTEB leaderboard + papers
RAG Systems | Retrieval: similarity search, hybrid search (BM25+dense) | ⭐⭐⭐⭐⭐ | Very High | 3h | ⬜ Not Started |  | Qdrant docs + tutorials
RAG Systems | Reranking: cross-encoders, Cohere Rerank, BGE Reranker | ⭐⭐⭐⭐⭐ | High | 2h | ⬜ Not Started |  | Cohere docs + cross-encoder paper
RAG Systems | Evaluation: RAGAS — faithfulness, recall, precision | ⭐⭐⭐⭐⭐ | Very High | 3h | ⬜ Not Started |  | RAGAS GitHub + paper
RAG Systems | Advanced: HyDE, Self-RAG, CRAG, Agentic RAG | ⭐⭐⭐⭐ | High | 4h | ⬜ Not Started |  | arxiv papers
AI Agents | ReAct pattern: reason + act loop architecture | ⭐⭐⭐⭐⭐ | 70% of new roles | 3h | ⬜ Not Started |  | ReAct paper (Yao et al.)
AI Agents | LangGraph: StateGraph, nodes, edges, conditional routing | ⭐⭐⭐⭐⭐ | Very High | 6h | ⬜ Not Started |  | LangGraph docs + tutorials
AI Agents | Multi-agent patterns: supervisor, hierarchical, debate | ⭐⭐⭐⭐⭐ | High | 4h | ⬜ Not Started |  | LangGraph multi-agent examples
AI Agents | Tool calling: function calling in OpenAI/Gemini/Anthropic | ⭐⭐⭐⭐⭐ | Every agent role | 3h | ⬜ Not Started |  | API docs for each provider
AI Agents | Human-in-the-loop: interrupt, approve, resume patterns | ⭐⭐⭐⭐ | High | 2h | ⬜ Not Started |  | LangGraph HITL docs
Vector Databases | HNSW, IVF, PQ algorithms — understand the math | ⭐⭐⭐⭐⭐ | 80% of RAG roles | 3h | ⬜ Not Started |  | Qdrant blog on algorithms
Vector Databases | Qdrant: collections, payloads, filtering, named vectors | ⭐⭐⭐⭐⭐ | High | 3h | ⬜ Not Started |  | Qdrant docs
Vector Databases | Pinecone, Weaviate, pgvector — pros and cons | ⭐⭐⭐⭐ | Medium | 2h | ⬜ Not Started |  | Comparison blog posts
MLOps | MLflow: experiment tracking, registry, model deployment | ⭐⭐⭐⭐⭐ | 60% of ML roles | 4h | ⬜ Not Started |  | MLflow docs
MLOps | Feast feature store: feature views, online/offline store | ⭐⭐⭐⭐ | Medium | 3h | ⬜ Not Started |  | Feast docs + tutorial
MLOps | Model monitoring: Evidently AI, drift detection, alerting | ⭐⭐⭐⭐ | Medium | 3h | ⬜ Not Started |  | Evidently docs
MLOps | CI/CD for ML: GitHub Actions, model testing patterns | ⭐⭐⭐⭐ | Medium | 3h | ⬜ Not Started |  | MLOps community guides
Cloud / Infra | GCP: Cloud Run, Vertex AI, BigQuery, GCS, IAM | ⭐⭐⭐⭐⭐ | Every GCP role | 5h | ⬜ Not Started |  | GCP learning path
Cloud / Infra | Docker: Dockerfile, multi-stage builds, compose | ⭐⭐⭐⭐⭐ | Almost every role | 3h | ⬜ Not Started |  | Docker official tutorial
Cloud / Infra | Kubernetes: pods, deployments, services, HPA basics | ⭐⭐⭐ | Medium | 3h | ⬜ Not Started |  | Kubernetes.io tutorial
Cloud / Infra | FastAPI: async, dependency injection, middleware, JWT | ⭐⭐⭐⭐⭐ | Every backend role | 4h | ⬜ Not Started |  | FastAPI official tutorial
System Design | ML System Design framework (7-step answer structure) | ⭐⭐⭐⭐⭐ | All senior roles | 5h | ⬜ Not Started |  | Chip Huyen 'Designing ML Systems'
System Design | Design recommendation systems (Netflix/YouTube type) | ⭐⭐⭐⭐⭐ | Very High | 4h | ⬜ Not Started |  | Engineering blogs (Netflix, Spotify)
System Design | Design real-time fraud detection system | ⭐⭐⭐⭐ | High | 3h | ⬜ Not Started |  | Practice with 7-step framework
System Design | Design LLM-powered enterprise search system | ⭐⭐⭐⭐⭐ | High | 4h | ⬜ Not Started |  | Practice with 7-step framework
System Design | CAP theorem, consistency models, distributed systems | ⭐⭐⭐ | Medium | 3h | ⬜ Not Started |  | Martin Kleppmann 'DDIA' book
Coding (LeetCode) | Arrays, Two Pointers, Sliding Window (20 problems) | ⭐⭐⭐⭐⭐ | Every coding round | 5h | ⬜ Not Started |  | LeetCode curated lists
Coding (LeetCode) | Hash Maps, Sets, Counting patterns (15 problems) | ⭐⭐⭐⭐⭐ | Very High | 4h | ⬜ Not Started |  | NeetCode roadmap
Coding (LeetCode) | Binary Search (10 problems) | ⭐⭐⭐⭐ | High | 3h | ⬜ Not Started |  | LeetCode binary search tag
Coding (LeetCode) | Trees, Graphs, BFS/DFS (15 problems) | ⭐⭐⭐⭐ | High | 4h | ⬜ Not Started |  | NeetCode roadmap
Coding (LeetCode) | Dynamic Programming medium (10 problems) | ⭐⭐⭐ | Medium | 4h | ⬜ Not Started |  | Neetcode DP playlist

## 📈 Weekly KPIs
📈 WEEKLY KPI DASHBOARD ¦ Track Your Progress Every Sunday
KPI Metric | W1 10–16 May | W2 17–23 May | W3 24–30 May | W4 31M–6J | W5 7–13 Jun | W6 14–20 Jun | W7 21–27 Jun | W8 28J–4J | W9 5–10 Jul | Total Target
Applications Sent | Target: 5 | Target: 15 | Target: 15 | Target: 15 | Target: 15 | Target: 15 | Target: 15 | Target: 10 | Target: 10 | 115 total
Response Rate % | Target: <1% | Target: 2–3% | Target: 3–5% | Target: 5%+ | Target: 5%+ | Target: 5%+ | Target: 7%+ | Target: 7%+ | Target: 7%+ | >5% avg
Recruiter Screens | Target: 0 | Target: 0–1 | Target: 1–2 | Target: 2–3 | Target: 2–3 | Target: 1–2 | Target: 1–2 | Target: 1–2 | Target: 1–2 | 10–17 total
Technical Rounds | Target: 0 | Target: 0 | Target: 0–1 | Target: 1–2 | Target: 2–3 | Target: 2–4 | Target: 2–4 | Target: 2–4 | Target: 1–3 | 10–21 total
Offers | Target: 0 | Target: 0 | Target: 0 | Target: 0 | Target: 0 | Target: 0–1 | Target: 0–2 | Target: 1–2 | Target: 1–3 | 1–3 total
Study Hours | Target: 20h | Target: 25h | Target: 25h | Target: 25h | Target: 25h | Target: 20h | Target: 20h | Target: 15h | Target: 10h | 185h+ total
LeetCode Problems | Target: 5 | Target: 10 | Target: 15 | Target: 20 | Target: 25 | Target: 30 | Target: 35 | Target: 40 | Target: 45 | 45+ total
LinkedIn Posts | Target: 1 | Target: 1 | Target: 1 | Target: 1 | Target: 1 | Target: 1 | Target: 1 | Target: 0 | Target: 0 | 8 posts
LinkedIn Connections | Target: 20 | Target: 20 | Target: 15 | Target: 10 | Target: 10 | Target: 5 | Target: 5 | Target: 5 | Target: 5 | 95+ new
GitHub Commits | Target: 10 | Target: 15 | Target: 20 | Target: 20 | Target: 15 | Target: 15 | Target: 15 | Target: 10 | Target: 5 | 125+ total
Projects Deployed | Target: 0 | Target: 0 | Target: 1 | Target: 2 | Target: 3 | Target: 4 | Target: 5 | Target: 5 | Target: 5 | 5 deployed
IIT Alumni Outreach | Target: 5 | Target: 10 | Target: 10 | Target: 10 | Target: 5 | Target: 5 | Target: 5 | Target: 5 | Target: 5 | 60+ alumni
✍️ WEEKLY ACTUAL VALUES — Fill in every Sunday during weekly review
KPI Metric | W1 10–16 May | W2 17–23 May | W3 24–30 May | W4 31M–6J | W5 7–13 Jun | W6 14–20 Jun | W7 21–27 Jun | W8 28J–4J | W9 5–10 Jul | Total Target
Applications Sent | [9 empty] | 0
Response Rate %
Recruiter Screens | [9 empty] | 0
Technical Rounds | [9 empty] | 0
Offers | [9 empty] | 0
Study Hours
LeetCode Problems | [9 empty] | 0
LinkedIn Posts | [9 empty] | 0
LinkedIn Connections | [9 empty] | 0
GitHub Commits | [9 empty] | 0
Projects Deployed | [9 empty] | 0
IIT Alumni Outreach | [9 empty] | 0