## 00_README
PavelBodle AI Startup Operating System
Complete Startup Execution OS — India AI Fintech ¦ Idea → MVP Launch
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Sheet Name | Purpose | Owner
WORKSPACE OVERVIEW
Startup | AI-powered Personal Finance Assistant & Insight Generation Platform
Target Market | Indian Families & Adults ¦ India-First Fintech AI
Platforms | Mobile App + Web App
Stage | Idea → MVP Launch
SHEET INDEX
00_README | This guide — workspace overview & navigation | Pavel
01_Founder_Hub | Founder command center — north-star metrics at a glance | Pavel
02_Master_Tasks | PMO-grade task tracker — all work streams | Pavel
03_Naming | Startup name ideation & trademark screening | Pavel
04_Legal | India-specific fintech legal & compliance tracker | Legal Lead
05_Product_Roadmap | Feature prioritization matrix + release planner | CPO
06_MVP_Sprint | Sprint planning & velocity tracker | Eng Lead
07_AI_ML | AI/ML model tracker + prompt engineering log | AI Lead
08_Engineering | Engineering task board + tech debt tracker | Eng Lead
09_Mobile_App | Mobile feature tracker (Android/iOS) | Mobile Lead
10_Web_App | Web frontend feature tracker | Frontend Lead
11_Backend | Backend & API tracker | Backend Lead
12_DevOps | DevOps, infra, CI/CD tracker | DevOps Lead
13_Hiring | Hiring pipeline + funnel dashboard | HR/Founder
14_Fundraising | Investor CRM + deal pipeline | Founder
15_Investors | Investor research & tracking list | Founder
16_Budget | Budget, burn rate & runway calculator | CFO/Founder
17_Revenue | Revenue model & projections | CFO/Founder
18_GTM | Go-to-market campaigns & marketing tracker | CMO
19_Content | Content calendar & social media planner | Content Lead
20_Feedback | User research & customer feedback log | PM/UX
21_War_Room | Launch operations & deployment tracker | All Leads
22_KPI_Dashboard | Live KPI dashboard — investor-ready metrics | Founder
23_Risk | Risk register & mitigation tracker | Founder
24_Meetings | Meeting notes & action items | All
25_Decisions | Decision log — key choices & rationale | Founder
26_SOPs | Standard operating procedures repository | Ops Lead
27_Competitors | Competitive analysis matrix | PM/Founder
28_User_Research | User interviews, personas & insights | UX/PM
29_Growth_Exp | Growth experiments & A/B test tracker | Growth Lead
💡 TIPS
Color Coding | 🔴 High Priority / Blocked ¦ 🟡 Medium / In Progress ¦ 🟢 Low / Done ¦ 🔵 Info
Status Values | Not Started → In Progress → Review → Done → Blocked
Formulas | All KPI cells use live formulas — update source data to auto-refresh dashboards
Dropdowns | Every Status/Priority/Owner column has a validated dropdown — click the cell
Automation | Connect Google Apps Script or Zapier to push Slack alerts on status changes
Import to GSheets | File → Import → Upload this .xlsx → Convert to Google Sheets format

## 01_Founder_Hub
PavelBodle ¦ Founder Command Center
North-Star Metrics · Sprint Status · Burn Rate · Top Risks
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
KEY METRICS — WEEK AT A GLANCE
Metric | Target | Current | Δ vs Last Week | Status | Owner | Notes
DAU (Daily Active Users) | 500 | 14 | -86 | On Track | Growth Lead | Targeting 500 by end of month
MAU | 2,000 | 14 | -486 | On Track | Growth Lead
Runway (months) | 18 | 14 | -1 | Watch | CFO | Fundraising in progress
Monthly Burn (₹) | ₹8L | ₹7.2L | -799964 | On Track | CFO | Under budget
Sprint Velocity (pts) | 40 | 36 | +4 | On Track | Eng Lead
Open Critical Bugs | 0 | 3 | +1 | At Risk | QA Lead | 2 in progress
AI Model Accuracy | 90% | 87% | +2% | On Track | AI Lead
Investor Meetings (MTD) | 5 | 3 | +1 | On Track | Founder | 2 more scheduled
Hiring Open Roles | 8 | 5 | 0 | On Track | HR
NPS Score | 50+ | 42 | +3 | Watch | PM | Beta feedback
SPRINT STATUS
Sprint | Goal | Start | End | Total Pts | Done Pts | % Complete | Status | Lead | Notes
Sprint 0 | Setup & Architecture | 2025-07-01 | 2025-07-14 | 30 | 30 | 100% | Done | Eng Lead | Completed on time
Sprint 1 | Auth + Onboarding | 2025-07-15 | 2025-07-28 | 40 | 32 | 80% | In Progress | Eng Lead | 2 tasks blocked
Sprint 2 | Expense Tracking MVP | 2025-07-29 | 2025-08-11 | 45 | 0 | 0% | Not Started | Eng Lead
Sprint 3 | AI Financial Insights | 2025-08-12 | 2025-08-25 | 50 | 0 | 0% | Not Started | AI Lead
Sprint 4 | UPI Integration | 2025-08-26 | 2025-09-08 | 40 | 0 | 0% | Not Started | Backend Lead
Sprint 5 | Beta Launch Prep | 2025-09-09 | 2025-09-22 | 35 | 0 | 0% | Not Started | All Leads
TOP 5 RISKS
Risk | Category | Likelihood | Impact | Score | Mitigation | Owner | Status
RBI sandbox approval delay | Legal | High | High | 9 | Engage RBI consultant early | Founder | Open
Key engineer departure | HR | Medium | High | 6 | ESOPs + retention plan | HR | Mitigating
LLM API cost overrun | Finance | Medium | Medium | 4 | Rate limits + caching layer | AI Lead | Open
Data breach / security flaw | Security | Low | Critical | 4 | Pentest before launch | DevOps Lead | Planned
Fundraising timeline slip | Finance | Medium | High | 6 | Parallel angel outreach | Founder | Open

## 02_Master_Tasks
PavelBodle ¦ Master Task Tracker
PMO-Grade Task Management — All Workstreams · All Sprints
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Task ID | Task Name | Department | Category | Sprint | Owner | Priority | Status | Progress % | Start Date | End Date | Days Left | Dependencies | Blockers | Est. Hours | Act. Hours | Est. Cost (₹) | Act. Cost (₹) | KPI Impact | Risk Level | Notes | Doc Link
T-001 | Setup GitHub repo & branch strategy | Engineering | Setup | Sprint 0 | Eng Lead | High | Done | 1 | 2025-07-01 | 2025-07-02 | 0 |  |  | 4 | 4 | 0 | 0 | Dev velocity | Low | Completed | github.com/repo
T-002 | Design system architecture | Engineering | Design | Sprint 0 | Arch Lead | High | Done | 1 | 2025-07-01 | 2025-07-05 | 0 | T-001 |  | 16 | 14 | 0 | 0 | System stability | Medium | ADR documented | notion.so/arch
T-003 | Figma UI Kit creation | Design | UI/UX | Sprint 0 | Designer | High | Done | 1 | 2025-07-03 | 2025-07-07 | 0 |  |  | 24 | 20 | 0 | 0 | User experience | Low |  | figma.com/kit
T-004 | User auth (OTP + Google SSO) | Engineering | Backend | Sprint 1 | Backend Dev | High | In Progress | 0.6 | 2025-07-15 | 2025-07-20 | 0 | T-002 |  | 20 | 12 | 0 | 0 | DAU | Medium | OTP SMS integration pending
T-005 | Onboarding flow — mobile | Mobile | Feature | Sprint 1 | Mobile Dev | High | In Progress | 0.4 | 2025-07-15 | 2025-07-21 | 0 | T-003,T-004 | SMS gateway | 24 | 10 | 0 | 0 | Activation rate | Medium
T-006 | Expense tracking UI | Mobile | Feature | Sprint 1 | Mobile Dev | High | Not Started | 0 | 2025-07-22 | 2025-07-28 | 0 | T-005 |  | 30 | 0 | 0 | 0 | DAU/Engagement | Low
T-007 | AI prompt engineering v1 | AI/ML | AI | Sprint 1 | AI Lead | High | In Progress | 0.3 | 2025-07-15 | 2025-07-25 | 0 | T-002 |  | 40 | 12 | 50000 | 0 | AI accuracy | High | Groq + Gemini Flash | notion.so/prompts
T-008 | Razorpay / UPI SDK integration | Backend | Integration | Sprint 4 | Backend Dev | High | Not Started | 0 | 2025-08-26 | 2025-09-05 | 0 | T-004 |  | 30 | 0 | 0 | 0 | Revenue | High | Need RBI sandbox
T-009 | Privacy policy + T&C drafting | Legal | Legal | Sprint 0 | Legal Lead | High | Done | 1 | 2025-07-01 | 2025-07-10 | 0 |  |  | 8 | 8 | 25000 | 25000 | Compliance | Low | Reviewed by lawyer | drive.google.com/tc
T-010 | Hire Senior React Native Dev | HR | Hiring | Sprint 0 | Founder | High | In Progress | 0.5 | 2025-07-05 | 2025-07-31 | 0 |  | Negotiation |  |  | 180000 | 0 | Dev velocity | Medium | 3 final candidates
T-011 | App Store developer accounts | DevOps | Setup | Sprint 1 | DevOps Lead | Medium | Done | 1 | 2025-07-15 | 2025-07-17 | 0 |  |  | 4 | 4 | 8300 | 8300 | Launch readiness | Low | Apple + Google
T-012 | GenAI insights dashboard — web | Web | Feature | Sprint 3 | Frontend Dev | Medium | Not Started | 0 | 2025-08-12 | 2025-08-22 | 0 | T-007 |  | 35 | 0 | 0 | 0 | Engagement | Medium
T-013 | Multi-language support (Hindi/Tamil) | Engineering | Feature | Sprint 4 | Full-Stack Dev | Medium | Not Started | 0 | 2025-08-26 | 2025-09-05 | 0 | T-005 |  | 20 | 0 | 0 | 0 | Retention | Low | i18n framework
T-014 | Financial health score algorithm | AI/ML | AI | Sprint 2 | AI Lead | High | Not Started | 0 | 2025-07-29 | 2025-08-08 | 0 | T-007 |  | 30 | 0 | 0 | 0 | Engagement | High
T-015 | DPIIT Startup India registration | Legal | Legal | Sprint 0 | Founder | Medium | In Progress | 0.7 | 2025-07-01 | 2025-07-31 | 0 |  |  | 4 | 3 | 5000 | 5000 | Fundraising | Low | MCA portal
Formulas:
Days Left = MAX(0,[End Date, row below]-TODAY())

## 03_Naming
Startup Naming Tracker
Brand Name Ideation, Screening & Trademark Status
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Name Idea | Meaning / Rationale | Domain (.com) | Domain (.in) | App Store Available | Trademark Status | Social Handles | Score (1-10) | Status | Notes
FinSaathi | Friend in finance (Hindi) | Check | Available | Yes | Clear | @finsaathi | 8 | Shortlisted | Saathi = companion
ArthAI | Arth = money/meaning (Sanskrit) | Taken | Available | Yes | Pending Check | @arthai_in | 7 | Shortlisted | Strong brand recall
PaisaGuru | Paisa = money (Hindi) | Available | Available | Yes | Clear | @paisaguru | 9 | Top Pick | Broad appeal
WealthSaathi | Wealth + companion | Available | Available | No | Pending | @wealthsaathi | 7 | Under Review | Longer name
FinDost | Fin + Dost (friend) | Available | Available | Yes | Clear | @findost | 8 | Shortlisted | Catchy
MoneyMitra | Money + Mitra (friend) | Taken | Check | Yes | Conflict | @moneymitra | 6 | Eliminated | Trademark conflict
NiveshAI | Nivesh = investment (Hindi) | Available | Available | Yes | Clear | @niveshai | 8 | Shortlisted | Investment focus
SmartKarcha | Smart + Karcha (expenses) | Available | Available | Yes | Clear | @smartkarcha | 7 | Under Review | Expense-focus angle

## 04_Legal
Legal & Compliance Tracker
India Fintech Compliance — MCA · GST · RBI · DPIIT · Data Protection
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Task | Category | Status | Owner | Deadline | Est. Cost (₹) | Vendor/Lawyer | Dependency | Risk | Notes
MCA Company Incorporation (Pvt Ltd) | Company Formation | Done | Founder | 2025-07-15 | 15000 | CS Firm | None | High | CIN obtained
GST Registration | Tax | In Progress | CFO | 2025-07-31 | 0 | Self/CA | MCA | Medium | ARN received
PAN & TAN for company | Tax | Done | CFO | 2025-07-20 | 0 | Self | MCA | Low | Both obtained
DPIIT Startup India Recognition | Incentives | In Progress | Founder | 2025-08-15 | 0 | Self | MCA | Medium | 75% complete
Trademark Registration (Brand Name) | IP | Pending | Legal Lead | 2025-09-01 | 10000 | IP Lawyer | Naming | High | After name finalized
Privacy Policy (DPDP Act 2023 compliant) | Data Privacy | Done | Legal Lead | 2025-07-25 | 25000 | Legal Firm | None | High | Published on website
Terms & Conditions | Legal | Done | Legal Lead | 2025-07-25 | 10000 | Legal Firm | None | Medium | Published
RBI NBFC/Payment Aggregator Advisory | Regulatory | In Progress | Legal Lead | 2025-09-30 | 50000 | RBI Consultant | None | Critical | Pre-application meeting done
PCI-DSS Compliance Planning | Security | Pending | DevOps Lead | 2025-10-01 | 30000 | Security Firm | Backend | High | Pre-assessment needed
Cybersecurity Policy (CERT-In) | Security | Pending | DevOps Lead | 2025-10-15 | 0 | Internal | DevOps | High | Mandatory for fintech
Employment Agreements | HR Legal | In Progress | HR | 2025-08-01 | 20000 | Legal Firm | Hiring | Medium | Template ready
Vendor Contracts (APIs, cloud) | Contracts | Pending | Ops Lead | 2025-09-01 | 15000 | Legal Firm | Engineering | Low | AWS, Twilio, etc.
MSME Udyam Registration | Incentives | Done | CFO | 2025-07-20 | 0 | Self | MCA | Low | Done
SEBI IASP Registration (if needed) | Regulatory | Pending | Legal Lead | 2026-01-01 | 100000 | SEBI Consultant | RBI | Critical | Investment advice angle
ISO 27001 Planning | Security | Pending | DevOps Lead | 2026-03-01 | 200000 | Certification Body | Post-MVP | Medium | Pre-MVP plan

## 05_Product_Roadmap
Product Roadmap
Feature Prioritization Matrix · MVP → V2 · Mobile + Web + Backend
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Feature Name | Feature Type | Platform | User Impact | Complexity | Effort (days) | Priority Score | Sprint | Owner | Design Status | Dev Status | QA Status | Release Version | Launch Readiness
User Onboarding & KYC | Core | Mobile + Web | High | Medium | 10 | 5 | Sprint 1 | Mobile Lead | Done | In Progress | Pending | v0.1 | 60%
Expense Tracking (manual) | Core | Mobile | High | Low | 7 | 7 | Sprint 1 | Mobile Lead | Done | In Progress | Pending | v0.1 | 55%
Smart Budget Planner | Core | Mobile + Web | High | Medium | 12 | 5 | Sprint 2 | Mobile Lead | In Progress | Not Started | Pending | v0.1 | 20%
AI Financial Assistant (chat) | AI | Mobile + Web | Critical | High | 20 | 6 | Sprint 3 | AI Lead | Draft | Not Started | Pending | v0.2 | 10%
Financial Health Score | AI | Mobile + Web | High | High | 15 | 3 | Sprint 3 | AI Lead | Draft | Not Started | Pending | v0.2 | 10%
UPI Bank Account Linking | Integration | Mobile | Critical | High | 18 | 6 | Sprint 4 | Backend Lead | Not Started | Not Started | Pending | v0.2 | 5%
Investment Insights | AI | Mobile + Web | Medium | High | 20 | 0 | Sprint 4 | AI Lead | Not Started | Not Started | Pending | v0.2 | 0%
Family Finance Dashboard | Core | Mobile + Web | High | High | 22 | 3 | Sprint 5 | Full-Stack | Not Started | Not Started | Pending | v0.3 | 0%
Goal Planning | Core | Mobile | Medium | Medium | 10 | 2 | Sprint 5 | Mobile Lead | Not Started | Not Started | Pending | v0.3 | 0%
Personalized Alerts | Core | Mobile | High | Low | 6 | 7 | Sprint 2 | Backend Lead | Not Started | Not Started | Pending | v0.1 | 0%
GenAI Insights Dashboard | AI | Web | High | High | 18 | 3 | Sprint 3 | Frontend Dev | Not Started | Not Started | Pending | v0.2 | 0%
Voice Assistant | AI | Mobile | Medium | Critical | 25 | -2 | Post-MVP | AI Lead | Not Started | Not Started | Pending | v1.0 | 0%
Multilingual Support (Hi/Ta/Te) | Core | Mobile + Web | High | Medium | 14 | 5 | Sprint 4 | Full-Stack | Not Started | Not Started | Pending | v0.2 | 0%
Document Analysis (AI) | AI | Mobile + Web | Medium | High | 20 | 0 | Post-MVP | AI Lead | Not Started | Not Started | Pending | v1.0 | 0%
Secure Document Vault | Security | Mobile + Web | Medium | Medium | 12 | 2 | Post-MVP | Backend Lead | Not Started | Not Started | Pending | v1.0 | 0%

## 06_MVP_Sprint
MVP Sprint Planner
Agile Sprint Tracker · Velocity · Burndown · Backlog
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
SPRINT SUMMARY
Sprint | Goal | Start | End | Capacity (pts) | Committed | Done | Velocity | % Complete | Status
Sprint 0 | Setup, Architecture, Legal | 2025-07-01 | 2025-07-14 | 30 | 30 | 30 | 30 | 3000% | Done
Sprint 1 | Auth, Onboarding, Expense UI | 2025-07-15 | 2025-07-28 | 40 | 40 | 22 | 22 | 2200% | In Progress
Sprint 2 | Budget, Alerts, Backend API | 2025-07-29 | 2025-08-11 | 45 | 45 | 0 | 0 | 0% | Not Started
Sprint 3 | AI Engine, Insights Dashboard | 2025-08-12 | 2025-08-25 | 50 | 50 | 0 | 0 | 0% | Not Started
Sprint 4 | UPI, Investment, Multilingual | 2025-08-26 | 2025-09-08 | 40 | 40 | 0 | 0 | 0% | Not Started
Sprint 5 | Beta Launch Prep, QA, Performance | 2025-09-09 | 2025-09-22 | 35 | 35 | 0 | 0 | 0% | Not Started
SPRINT BACKLOG — SPRINT 1
Story ID | User Story | Points | Priority | Owner | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Notes
US-001 | As a user I can register with mobile OTP | 5 | High | Backend Dev | Done | 5 | 5 | 5 | 5 | 0 | Completed D3
US-002 | As a user I can log in with Google SSO | 3 | High | Backend Dev | Done | 3 | 3 | 0 | 0 | 0 | Completed D2
US-003 | As a user I see onboarding screens | 5 | High | Mobile Dev | In Progress | 5 | 5 | 5 | 5 | 3 | 90% done
US-004 | As a user I can add manual expense | 8 | High | Mobile Dev | In Progress | 8 | 8 | 8 | 6 | 4 | Category picker pending
US-005 | As a user I see expense categories | 3 | Medium | Mobile Dev | Not Started |  |  |  |  | 3
US-006 | As a user I can set a monthly budget | 5 | Medium | Mobile Dev | Not Started |  |  |  |  | 5 | Carry to S2
US-007 | AI prompt: classify expense category | 8 | High | AI Lead | In Progress | 8 | 8 | 8 | 8 | 5 | Groq API integrated
US-008 | Backend: expense CRUD API | 5 | High | Backend Dev | Done | 5 | 5 | 0 | 0 | 0 | Completed D2
US-009 | Push notification service setup | 3 | Medium | Backend Dev | Not Started |  |  |  |  | 3 | Firebase FCM
US-010 | Analytics event tracking (Mixpanel) | 2 | Low | Full-Stack | Not Started |  |  |  |  | 2
VELOCITY METRICS
Average Velocity (pts/sprint) | 0
Total Points Committed | 0
Total Points Done | 0
Overall % Complete | 0%
Sprints Remaining | 4
Estimated MVP Date | 2025-09-22

## 07_AI_ML
AI/ML Tracker
Models · Prompts · RAG Pipeline · Experiments · Evaluation
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
MODEL REGISTRY
Model Name | Use Case | LLM / API | Prompt Ver. | Dataset | Accuracy | Latency (ms) | Cost/Req (₹) | Eval Score | Hallucination Risk | Deploy Status | Monitoring | Feedback Score
expense-classifier-v1 | Classify expense category | Groq/Llama3-8b | v1.2 | Internal 5k rows | 88% | 320 | 0.02 | 7.5/10 | Low | Production | DataDog | 4.1/5
budget-advisor-v1 | AI budget recommendations | Gemini 2.0 Flash | v1.0 | N/A (zero-shot) | 82% | 450 | 0.05 | 6.8/10 | Medium | Staging | Langfuse | 3.9/5
financial-health-score | Compute financial health | Custom rule + LLM | v0.5 | 50 user profiles | 79% | 200 | 0.01 | 6.2/10 | Low | Dev | None | N/A
investment-insight-gen | Generate investment insights | Gemini 2.0 Flash | v0.3 | NSE/BSE data | 75% | 600 | 0.08 | 6.0/10 | High | Dev | None | N/A
multilingual-NLU | Hindi/Tamil NLU | IndicBERT fine-tune | v0.1 | IndicGLUE | 71% | 150 | 0.00 | 5.5/10 | Medium | Planned | None | N/A
doc-analyzer | Analyze financial docs | Gemini 2.0 Flash Vision | v0.2 | 50 sample docs | 80% | 1200 | 0.15 | 6.5/10 | Medium | Planned | None | N/A
PROMPT ENGINEERING LOG
Prompt ID | Use Case | Version | Model | Technique | Accuracy | Tokens (avg) | Cost/Run (₹) | Evaluation | Status | Author | Date | Notes
P-001 | Expense classification | v1.2 | Groq/Llama3 | Few-shot + CoT | 88% | 420 | 0.02 | Pass | Active | AI Lead | 2025-07-15 | Best so far
P-002 | Budget recommendation | v1.0 | Gemini Flash | Zero-shot | 82% | 350 | 0.05 | Pass | Active | AI Lead | 2025-07-18 | Needs improvement
P-003 | Financial advice generation | v0.3 | Gemini Flash | RAG + prompt | 79% | 800 | 0.12 | Partial | Testing | AI Lead | 2025-07-20 | RAG context helps
P-004 | Expense summary narrative | v0.2 | Groq/Llama3 | Template fill | 85% | 200 | 0.01 | Pass | Active | AI Lead | 2025-07-17 | High quality output
P-005 | Goal planning assistant | v0.1 | Gemini Flash | Chain-of-thought | 77% | 600 | 0.09 | Fail | Retired | AI Lead | 2025-07-12 | Too generic
RAG PIPELINE TRACKER
Pipeline Name | Data Source | Chunking | Embedding Model | Vector DB | Retrieval K | Retrieval Score | Reranker | Response Quality | Status | Owner | Cost/Mo (₹) | Notes
Expense Q&A RAG | User transaction history | 512 tokens overlap 50 | text-embedding-3-small | ChromaDB | 5 | 0.82 | No | Good | Active | AI Lead | 500 | Local ChromaDB
Financial News RAG | NSE/BSE + news feeds | 1024 tokens | text-embedding-3-small | FAISS | 8 | 0.75 | Yes (cohere) | Good | Staging | AI Lead | 1200 | Scheduled refresh
Document Analysis RAG | User uploaded PDFs | Page-level | Gemini Embedding | ChromaDB | 3 | 0.88 | No | Excellent | Active | AI Lead | 800 | Gemini Vision + RAG

## 08_Engineering
Engineering Tracker
Tech Debt · Architecture Decisions · Code Review · Infra
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Task ID | Task Name | Type | Component | Sprint | Owner | Priority | Status | PR Link | Tech Debt Score | Complexity | Notes
E-001 | Setup monorepo (Turborepo) | Setup | All | Sprint 0 | Arch Lead | High | Done | github.com/pr/1 | Low | Medium | Nx considered, chose Turborepo
E-002 | FastAPI backend scaffold | Backend | API | Sprint 0 | Backend Lead | High | Done | github.com/pr/2 | Low | Low | Python 3.11, async
E-003 | React Native app scaffold | Mobile | App | Sprint 0 | Mobile Lead | High | Done | github.com/pr/3 | Low | Low | Expo + TypeScript
E-004 | Next.js web scaffold | Web | Frontend | Sprint 0 | Frontend Dev | High | Done | github.com/pr/4 | Low | Low | Next 14 App Router
E-005 | PostgreSQL + Redis setup | Database | Backend | Sprint 0 | Backend Lead | High | Done | github.com/pr/5 | Low | Low | Supabase managed PG
E-006 | JWT auth middleware | Backend | API | Sprint 1 | Backend Dev | High | Done | github.com/pr/8 | Low | Low | RS256 tokens
E-007 | Expense API CRUD | Backend | API | Sprint 1 | Backend Dev | High | Done | github.com/pr/9 | Low | Low | Full REST + validation
E-008 | Refactor expense model (schema v2) | Tech Debt | Database | Sprint 2 | Backend Dev | Medium | Planned |  | Medium | Medium | V1 schema has nullability issues
E-009 | Add request rate limiting | Security | API | Sprint 2 | Backend Dev | High | Planned |  | Low | Low | Redis sliding window
E-010 | Unit test coverage to 80% | Quality | All | Sprint 3 | All Devs | Medium | Planned |  | Medium | Low | Currently 34%
E-011 | CI/CD pipeline (GitHub Actions) | DevOps | Infra | Sprint 1 | DevOps Lead | High | In Progress |  | Low | Medium | Deploy to Railway
E-012 | OpenTelemetry instrumentation | Observability | All | Sprint 3 | DevOps Lead | Medium | Planned |  | Low | Medium | Traces + metrics

## 09_Mobile_App
Mobile App Tracker
React Native · iOS + Android · Feature Status · Build Tracker
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Feature ID | Feature Name | Screen | Platform | Sprint | Owner | Status | Design Link | Build Version | Test Status | Notes | Dependencies
M-001 | Splash Screen + Logo | Splash | iOS + Android | Sprint 0 | Mobile Dev | Done | figma.com/s1 | 0.0.1 | Passed
M-002 | Onboarding Flow (4 screens) | Onboarding | iOS + Android | Sprint 1 | Mobile Dev | In Progress | figma.com/s2 | 0.1.0 | Pending | 90% done | T-005
M-003 | OTP Login Screen | Auth | iOS + Android | Sprint 1 | Mobile Dev | Done | figma.com/s3 | 0.1.0 | Passed |  | T-004
M-004 | Home / Dashboard Screen | Home | iOS + Android | Sprint 2 | Mobile Dev | Not Started | figma.com/s4 |  | Pending |  | M-003
M-005 | Add Expense Screen | Expense | iOS + Android | Sprint 1 | Mobile Dev | In Progress | figma.com/s5 | 0.1.0 | Pending | Category picker WIP | M-004
M-006 | Expense List + Filter | Expense | iOS + Android | Sprint 2 | Mobile Dev | Not Started | figma.com/s6 |  | Pending |  | M-005
M-007 | Budget Setup Screen | Budget | iOS + Android | Sprint 2 | Mobile Dev | Not Started | figma.com/s7 |  | Pending |  | M-006
M-008 | AI Chat Screen | AI | iOS + Android | Sprint 3 | Mobile Dev | Not Started | figma.com/s8 |  | Pending |  | T-007
M-009 | Financial Health Score Card | AI | iOS + Android | Sprint 3 | Mobile Dev | Not Started | figma.com/s9 |  | Pending |  | T-014
M-010 | Goal Planner Screen | Goals | iOS + Android | Sprint 5 | Mobile Dev | Not Started | figma.com/s10 |  | Pending |  | M-007
M-011 | Notifications + Alerts | Notifications | iOS + Android | Sprint 2 | Mobile Dev | Not Started | figma.com/s11 |  | Pending | Firebase FCM | T-011
M-012 | Profile & Settings | Settings | iOS + Android | Sprint 3 | Mobile Dev | Not Started | figma.com/s12 |  | Pending |  | M-003
M-013 | Bank Linking Screen (UPI) | Integration | Android | Sprint 4 | Mobile Dev | Not Started | figma.com/s13 |  | Pending | Android first | T-008
M-014 | Investment Insights Screen | Investment | iOS + Android | Sprint 4 | Mobile Dev | Not Started | figma.com/s14 |  | Pending |  | T-007

## 10_Web_App
Web App Tracker
Next.js 14 · Feature Status · Page Builder · SEO
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Page/Feature | Route | Type | Sprint | Owner | Status | Design Link | SEO Priority | Analytics | Notes | Dependencies
Landing Page | / | Marketing | Sprint 0 | Frontend Dev | Done | figma.com/w1 | High | GA4 + Hotjar | Convert visitors
Pricing Page | /pricing | Marketing | Sprint 1 | Frontend Dev | In Progress | figma.com/w2 | High | GA4 | Freemium model
Auth / Sign In | /auth | App | Sprint 1 | Frontend Dev | In Progress | figma.com/w3 | Low | GA4 | OTP + Google | T-004
Dashboard Home | /app/dashboard | App | Sprint 2 | Frontend Dev | Not Started | figma.com/w4 | Low | Mixpanel | North-star screen | M-004
Expense Manager | /app/expenses | App | Sprint 2 | Frontend Dev | Not Started | figma.com/w5 | Low | Mixpanel | Tabular + charts | M-005
Budget Planner | /app/budget | App | Sprint 2 | Frontend Dev | Not Started | figma.com/w6 | Low | Mixpanel |  | M-007
AI Insights Dashboard | /app/ai | App | Sprint 3 | Frontend Dev | Not Started | figma.com/w7 | Low | Mixpanel | GenAI charts | T-007
Investment Insights | /app/invest | App | Sprint 4 | Frontend Dev | Not Started | figma.com/w8 | Low | Mixpanel |  | T-007
Family Finance Hub | /app/family | App | Sprint 5 | Frontend Dev | Not Started | figma.com/w9 | Low | Mixpanel | Multi-user
Goals Tracker | /app/goals | App | Sprint 5 | Frontend Dev | Not Started | figma.com/w10 | Low | Mixpanel
Profile & Settings | /app/settings | App | Sprint 3 | Frontend Dev | Not Started | figma.com/w11 | Low | Mixpanel
Blog / Financial Tips | /blog | Marketing | Sprint 5 | Content Lead | Not Started |  | High | GA4 + GSC | SEO content

## 11_Backend
Backend & API Tracker
FastAPI · PostgreSQL · Redis · Microservices · Integrations
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
API/Service | Method | Endpoint | Sprint | Owner | Status | Auth Required | Rate Limit | Tested | Notes | Dependencies
User Registration | POST | /api/v1/auth/register | Sprint 1 | Backend Dev | Done | No | 100/hr | Yes | OTP triggered
User Login (OTP verify) | POST | /api/v1/auth/verify-otp | Sprint 1 | Backend Dev | Done | No | 50/hr | Yes | JWT returned
Google OAuth | GET | /api/v1/auth/google | Sprint 1 | Backend Dev | Done | No | 100/hr | Yes
Get User Profile | GET | /api/v1/user/profile | Sprint 1 | Backend Dev | Done | Yes | 200/hr | Yes |  | T-004
Create Expense | POST | /api/v1/expenses | Sprint 1 | Backend Dev | Done | Yes | 500/hr | Yes
List Expenses | GET | /api/v1/expenses | Sprint 1 | Backend Dev | Done | Yes | 500/hr | Yes | Pagination+filter
Update Expense | PATCH | /api/v1/expenses/{id} | Sprint 1 | Backend Dev | Done | Yes | 200/hr | Yes
Delete Expense | DELETE | /api/v1/expenses/{id} | Sprint 1 | Backend Dev | Done | Yes | 200/hr | Yes | Soft delete
AI Chat Endpoint | POST | /api/v1/ai/chat | Sprint 3 | AI Lead | Planned | Yes | 30/hr | No | LangChain router | T-007
Financial Health Score | GET | /api/v1/ai/health-score | Sprint 3 | AI Lead | Planned | Yes | 100/hr | No |  | T-014
UPI Bank Link (Plaid-like) | POST | /api/v1/banking/link | Sprint 4 | Backend Dev | Planned | Yes | 10/hr | No | RBI sandbox needed | T-008
Get Investment Data | GET | /api/v1/invest/insights | Sprint 4 | AI Lead | Planned | Yes | 100/hr | No | NSE/BSE feed
Create Budget | POST | /api/v1/budget | Sprint 2 | Backend Dev | Planned | Yes | 100/hr | No
Get Notifications | GET | /api/v1/notifications | Sprint 2 | Backend Dev | Planned | Yes | 500/hr | No | FCM webhook

## 12_DevOps
DevOps Tracker
CI/CD · Infrastructure · Monitoring · Security · Cloud
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Task | Category | Environment | Sprint | Owner | Status | Tool/Service | Cost/Mo (₹) | Uptime SLA | Notes | Priority
GitHub Actions CI pipeline | CI/CD | All | Sprint 1 | DevOps Lead | In Progress | GitHub Actions | 0 | N/A | Build + test on PR | High
Railway backend deployment | Deploy | Production | Sprint 1 | DevOps Lead | Done | Railway.app | 2000 | 99.5% | FastAPI auto-deploy | High
Vercel web deployment | Deploy | Production | Sprint 0 | DevOps Lead | Done | Vercel | 0 | 99.9% | Next.js auto-deploy | High
Supabase PostgreSQL | Database | Production | Sprint 0 | DevOps Lead | Done | Supabase | 0 | 99.9% | Free tier 500MB | High
Redis (Upstash) | Cache | Production | Sprint 1 | DevOps Lead | Done | Upstash | 0 | 99.5% | Serverless Redis free | Medium
AWS S3 (document storage) | Storage | Production | Sprint 2 | DevOps Lead | Planned | AWS S3 | 400 | 99.9% | 5GB free tier | Medium
DataDog APM | Monitoring | Production | Sprint 3 | DevOps Lead | Planned | DataDog | 0 | N/A | Free tier 5 hosts | Medium
Sentry error tracking | Monitoring | All | Sprint 1 | DevOps Lead | Done | Sentry | 0 | N/A | Free 5K events/mo | High
Expo EAS Build (mobile) | CI/CD | Mobile | Sprint 1 | Mobile Dev | In Progress | Expo EAS | 0 | N/A | Free 30 builds/mo | High
Cloudflare CDN + WAF | Security | Production | Sprint 2 | DevOps Lead | Planned | Cloudflare | 0 | 99.99% | Free plan | High
GitHub Dependabot | Security | Dev | Sprint 1 | DevOps Lead | Done | GitHub | 0 | N/A | Auto-dependency updates | Medium
Backup strategy (DB + S3) | Backup | Production | Sprint 3 | DevOps Lead | Planned | Supabase + S3 | 200 | N/A | Daily automated backups | High
Load testing (k6) | Performance | Staging | Sprint 5 | Backend Dev | Planned | k6 | 0 | N/A | 100 concurrent users | Medium
SSL certificates | Security | Production | Sprint 0 | DevOps Lead | Done | Let's Encrypt | 0 | N/A | Auto-renewed | High

## 13_Hiring
Hiring Pipeline
Talent Acquisition · Interview Funnel · Offer Tracker
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
OPEN ROLES
Role | Department | JD Link | Applications | Phone Screen | Technical | Final | Offers | Hired | Budget (₹/mo) | Status | Priority
Senior React Native Developer | Engineering | notion.so/jd1 | 12 | 5 | 3 | 2 | 1 | 1 | 120000 | Filled | High
Backend Engineer (Python/FastAPI) | Engineering | notion.so/jd2 | 18 | 6 | 4 | 2 | 1 | 0 | 110000 | Interviewing | High
AI/ML Engineer | AI/ML | notion.so/jd3 | 8 | 3 | 2 | 1 | 0 | 0 | 130000 | Interviewing | Critical
Product Designer (UI/UX) | Design | notion.so/jd4 | 15 | 5 | 3 | 1 | 0 | 0 | 90000 | Interviewing | High
Growth / Marketing Manager | Marketing | notion.so/jd5 | 20 | 6 | 3 | 2 | 1 | 0 | 80000 | Offer Stage | High
Data Analyst | Data | notion.so/jd6 | 10 | 3 | 2 | 0 | 0 | 0 | 70000 | Sourcing | Medium
DevOps / Platform Engineer | Engineering | notion.so/jd7 | 5 | 2 | 1 | 0 | 0 | 0 | 100000 | Sourcing | Medium
Customer Success Executive | Operations | notion.so/jd8 | 25 | 8 | 0 | 0 | 0 | 0 | 50000 | Sourcing | Low
CANDIDATE PIPELINE
Candidate Name | Role | Source | Resume | Tech Score | Interview Stage | Salary Exp (₹) | Location | Notice Period | Status | Joining Date | Notes
Arjun Sharma | Senior React Native Dev | LinkedIn | drive.google.com/r1 | 8.5/10 | Offer | 125000 | Bangalore | 30 days | Offer Accepted | 2025-08-01 | Strong portfolio
Priya Nair | Backend Engineer | Naukri | drive.google.com/r2 | 7.8/10 | Final | 115000 | Mumbai | Immediate | Final Interview |  | Good FastAPI exp
Rahul Verma | AI/ML Engineer | AngelList | drive.google.com/r3 | 9.2/10 | Technical | 135000 | Hyderabad | 60 days | Technical |  | LLM + LangChain exp
Sneha Iyer | Product Designer | Behance | drive.google.com/r4 | 8.0/10 | Final | 95000 | Bangalore | 30 days | Final Interview |  | Fintech portfolio
Kiran Patel | Growth Manager | Referral | drive.google.com/r5 | 7.5/10 | Offer | 85000 | Ahmedabad | 15 days | Offer Sent |  | Ex-Groww
Divya Mehta | AI/ML Engineer | Twitter | drive.google.com/r6 | 8.8/10 | Phone Screen | 140000 | Pune | 45 days | Phone Screen |  | MS from IIT
Arun Kumar | Backend Engineer | iimjobs | drive.google.com/r7 | 6.5/10 | Rejected | 100000 | Chennai | Immediate | Rejected |  | Insufficient exp
HIRING METRICS
Total Applications | 0
Total Hired | 0
Offer Acceptance Rate | 0%
Avg Tech Score (pipeline) | 0
Open Roles | 6
Total Monthly Salary Budget (₹) | 0

## 14_Fundraising
Fundraising CRM
Investor Pipeline · Deal Flow · Follow-ups · Status Tracker
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
# | Investor Name | Firm | Sector Focus | Stage | Contact Source | Warm Intro | Email | LinkedIn | Last Contact | Follow-up Date | Interest Level | Meeting Status | Deck Shared | Current Status | Notes
1 | Anand Lunia | India Quotient | Fintech/Consumer | Pre-Seed/Seed | Portfolio founder | Yes | anand@iq.vc | linkedin.com/anand | 2025-07-20 | 2025-08-05 | High | 1st meeting done | Yes | Warm Lead | Likes the AI angle
2 | Shekhar Kirani | Accel India | Fintech/SaaS | Seed | Cold email | No | shekhar@accel.com | linkedin.com/shekhar | 2025-07-15 | 2025-07-30 | Medium | Deck reviewed | Yes | Follow-up | Wants traction data
3 | Prashanth Prakash | Accel India | Fintech | Series A | Referral | Yes | prashanth@accel.com | linkedin.com/pp | 2025-07-18 | 2025-08-10 | Medium | Intro call | Yes | Interested | Series A focus — early
4 | Vikram Vaidyanathan | Matrix Partners | Fintech/AI | Seed | LinkedIn | No | vikram@matrix.in | linkedin.com/vv | 2025-07-10 | 2025-07-28 | Low | No response | Yes | Cold | Follow up needed
5 | Karan Mohla | B Capital | AI/ML | Seed | Conf meet | Yes | karan@bcapital.com | linkedin.com/km | 2025-07-22 | 2025-08-01 | High | Partner meeting | Yes | Hot Lead | Loves AI + fintech combo
6 | Rehan Yar Khan | Orios Venture | Fintech/Consumer | Pre-Seed | Angel referral | Yes | rehan@orios.in | linkedin.com/rk | 2025-07-12 | 2025-07-26 | High | 2nd meeting | Yes | Term Sheet Pending | Checking legal setup
7 | Rajan Anandan | Sequoia Capital | Fintech/AI | Series A | Cold outreach | No | rajan@sequoiacap.com | linkedin.com/ra |  | 2025-08-15 | Low | Not contacted | No | Pipeline | Build traction first
8 | Nikhil Kamath (Angel) | Independent | Fintech/Crypto | Angel | Twitter DM | No | nikhil@zerodha.com | linkedin.com/nk | 2025-07-05 | 2025-07-20 | Medium | DM responded | Yes | Interested | Intro call scheduled
9 | Arpit Agarwal | Blume Ventures | Fintech | Seed | YC referral | Yes | arpit@blume.vc | linkedin.com/aa | 2025-07-17 | 2025-07-31 | High | DD Started | Yes | Due Diligence | Financial model requested
10 | Sanjay Mehta | 100X.VC | Fintech | Pre-Seed | Application | No | sanjay@100x.vc | linkedin.com/sm | 2025-07-08 | 2025-07-22 | Medium | Phone call | Yes | Follow-up | 100X cohort application
FUNDRAISING SUMMARY
Target Raise (₹ Cr) | 2.0
Raised to Date (₹ Cr) | 0
Total Investors Contacted | 10
Hot / Warm Leads | 4
Term Sheets | 1
Due Diligence | 1
Closed Won | 0

## 15_Investors
Investor Research
VC Firms · Angels · Family Offices · India Fintech Ecosystem
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Investor / Firm | Type | Stage Focus | Ticket Size (₹ Cr) | Sector | Portfolio Cos. | Website | Warm Intro Source | Priority | Notes
India Quotient | VC | Pre-Seed/Seed | 0.5-3 | Consumer/Fintech | DealShare, BankSathi | iq.vc | High | A1 | Best fit for India consumer fintech
Accel India | VC | Seed/Series A | 3-20 | Fintech/SaaS | Bharatpe, Zetwerk | accel.com/india | Medium | A | Strong fintech portfolio
Matrix Partners | VC | Seed/Series A | 3-15 | Fintech | Ola, Razorpay | matrixpartners.in | Low | B | More growth stage
Blume Ventures | VC | Pre-Seed/Seed | 0.5-5 | AI/Fintech | Unacademy, Purplle | blume.vc | High | A | Very AI-positive thesis
100X.VC | VC | Pre-Seed | 0.25-0.75 | All Sectors | 50+ startups | 100x.vc | High | A | Good for first check
Orios Venture Partners | VC | Seed | 1-5 | Consumer/Fintech | Xpressbees | orios.in | High | A | India-focused consumer
Sequoia Capital India | VC | Series A+ | 10-50 | Fintech/AI | Razorpay, CRED | sequoiacap.com/india | Low | C | Too early for them
B Capital Group | VC | Seed/Series A | 5-20 | AI/Fintech | Various | bcapital.com | Medium | B | Strong AI thesis
Kunal Shah (Angel) | Angel | Pre-Seed | 0.25-1 | Fintech | CRED |  | High | A1 | Ex-CRED, knows fintech deeply
Nikhil Kamath (Angel) | Angel | Pre-Seed | 0.25-1 | Fintech/Invest | Zerodha ecosystem |  | Medium | B | Reach via Twitter
Zerodha Fund House | CVC | Seed | 1-3 | Fintech/Invest |  | zerodha.com | Medium | B | Strategic investor angle
PayU Fintech Fund | CVC | Seed | 2-8 | Payments/Fintech | Various | payu.in | Low | C | Corporate VC — slow

## 16_Budget
Budget & Burn Rate
Monthly Burn · Runway · Cost Centers · Actuals vs Forecast
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
MONTHLY BUDGET vs ACTUALS (₹)
Category | Sub-category | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Q3 Budget | Q3 Actual | Q4 Budget | Variance
Engineering | Salaries | 300000 | 310000 | 320000 | 330000 | 330000 | 330000 | 0 | 0 | 0 | 0
AI/ML | LLM API Costs | 20000 | 25000 | 30000 | 35000 | 40000 | 40000 | 0 | 0 | 0 | 0
AI/ML | GPU/Compute | 10000 | 10000 | 15000 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0
Infrastructure | Cloud (Railway/AWS) | 8000 | 10000 | 12000 | 15000 | 20000 | 25000 | 0 | 0 | 0 | 0
Legal | Registration & Compliance | 75000 | 20000 | 15000 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0
Marketing | Digital Marketing | 0 | 50000 | 80000 | 100000 | 120000 | 150000 | 0 | 0 | 0 | 0
Design | Tools + Freelance | 15000 | 15000 | 15000 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0
Operations | Office + Misc | 10000 | 10000 | 12000 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0
Software | SaaS Tools (Notion,Figma,etc) | 12000 | 12000 | 12000 | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0
Travel | Investor meetings | 5000 | 10000 | 15000 | 20000 | 20000 | 15000 | 0 | 0 | 0 | 0
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RUNWAY CALCULATOR
Starting Cash (₹) | 5000000
Monthly Burn Rate (₹) | 0
Runway (months) | 999
Estimated Runway End | May-2026
Revenue (Monthly, ₹) | 50000
Net Burn (₹/mo) | 0
Adjusted Runway (months) | 999
Formulas:
Sub-category = TEXT(TODAY()+[Jul-25, row above]*30,"MMM-YYYY")

## 17_Revenue
Revenue Model
Freemium + Subscription · Unit Economics · 12-Month Projections
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
PRICING TIERS
Tier | Price (₹/mo) | Features | Target Users | Conv. Rate | Notes
Free | 0 | Basic tracking, 50 txns/mo, 1 AI insight/wk | All users | N/A | Acquisition tier
Plus | 199 | Unlimited tracking, 10 AI insights/wk, Budgeting | Active savers | 8% | Core revenue tier
Pro | 499 | All features, AI advisor, UPI, doc analysis | Power users | 2% | Premium tier
Family | 799/mo | 5 members, family dashboard, all Pro features | Families | 1% | High LTV tier
12-MONTH REVENUE PROJECTION
Month | Free Users | Plus Subs | Pro Subs | Family Subs | MRR (₹) | ARR (₹) | CAC (₹) | LTV (₹) | LTV:CAC
Month 1 (Oct-25) | 500 | 20 | 5 | 2 | 8073 | 96876 | 800 | 1671.6 | 0.008258
Month 2 | 800 | 40 | 12 | 5 | 17943 | 215316 | 750 | 1671.6 | 1671.6
Month 3 | 1200 | 70 | 22 | 9 | 32099 | 385188 | 700 | 1671.6 | 1671.6
Month 6 | 4000 | 300 | 90 | 40 | 136570 | 1638840 | 600 | 1671.6 | 1671.6
Month 9 | 10000 | 900 | 250 | 100 | 383750 | 4605000 | 500 | 1671.6 | 1671.6
Month 12 | 22000 | 2200 | 600 | 250 | 936950 | 11243400 | 450 | 1671.6 | 1671.6

## 18_GTM
GTM & Marketing
Go-to-Market Campaigns · CAC · Channels · Growth Experiments
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Campaign Name | Channel | Budget (₹) | Spend (₹) | Impressions | Clicks | Signups | CAC (₹) | CTR | Conv Rate | ROI | Status | Owner
Launch Waitlist Campaign | Instagram + Facebook | 50000 | 45000 | 250000 | 8500 | 420 | 45000 | 850000% | 42000% | 38580 | Done | CMO
Google Search — Finance Tips | Google Ads | 30000 | 28000 | 45000 | 2200 | 180 | 28000 | 220000% | 18000% | 7820 | Done | CMO
Influencer — YouTube (fin-ed) | YouTube | 20000 | 20000 | 180000 | 5500 | 210 | 20000 | 550000% | 21000% | 21790 | Done | CMO
Referral Program — Beta | In-App | 10000 | 3000 |  | 1200 | 380 | 3000 |  | 38000% | 72620 | Active | Growth Lead
WhatsApp Broadcast — Family | WhatsApp | 5000 | 2000 |  | 2000 | 320 | 2000 |  | 32000% | 61680 | Active | CMO
SEO Blog — Tax tips India | Organic SEO | 0 | 0 |  | 800 | 65 | 0 |  | 6500% | N/A | In Progress | Content Lead
App Store Optimization | ASO | 0 | 0 | 12000 | 800 | 150 | 0 | 80000% | 15000% | N/A | Planned | Mobile Dev
LinkedIn — B2B (HR benefits) | LinkedIn Ads | 15000 | 0 |  |  | 0 | 0 |  |  |  | Planned | CMO
CHANNEL SCORECARD
Channel | Total Spend (₹) | Total Signups | Avg CAC (₹) | Best Performing? | Notes
Social (IG+FB) | 0 | 0 | 0 | Yes | Lowest CAC channel
Google Ads | 30000 | 180 | 30000 | No | High intent but expensive
Referral | 10000 | 380 | 10000 | Yes | Best CAC — scale this
Organic SEO | 0 | 65 | 0 | No | Long-term play

## 19_Content
Content Calendar
Social Media · Blog · YouTube · WhatsApp · Email Newsletter
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Date | Content Title | Type | Platform | Format | CTA | Owner | Status | Reach | Engagement | Notes
2025-08-01 | 5 Tax Saving Tips for Salaried Indians | Education | Instagram | Carousel | Download App | Content Lead | Published | 12000 | 4.2% | Top performer
2025-08-03 | How AI Can Manage Your Budget | Awareness | YouTube | Reel (60s) | Subscribe | CMO | Published | 8500 | 6.1% | High shares
2025-08-05 | Financial Health Score — What Is It? | Product Feature | LinkedIn | Article | Sign Up Waitlist | Founder | Published | 3200 | 3.8% | Good B2B reach
2025-08-07 | UPI + AI = Your Personal CFO | Awareness | Twitter/X | Thread | App Download | Growth Lead | Scheduled
2025-08-08 | India's Best Budgeting Apps (Feature) | SEO Blog | Website | Blog 1500w | Sign Up | Content Lead | Draft |  |  | SEO target: budgeting apps India
2025-08-10 | Family Finance Tips — Hindi | Education | WhatsApp | Message + Image | Share | Content Lead | Planned |  |  | Regional language content
2025-08-12 | August Newsletter — AI Finance Digest | Newsletter | Email | HTML Email | Upgrade to Pro | CMO | Planned |  |  | 5000 subscribers target
2025-08-14 | Behind the Build: Our AI Model | Behind Scenes | LinkedIn | Post + Video | Follow | Founder | Planned |  |  | Founder branding
2025-08-17 | Expense Tracking Challenge #30Days | Community | Instagram | Story Series | Tag a Friend | Growth Lead | Planned |  |  | Viral campaign
2025-08-20 | How Indians Waste ₹5000/Month | Hook Content | YouTube Shorts | Short 30s | App Download | CMO | Planned |  |  | Hook-based content

## 20_Feedback
Customer Feedback & User Research
Beta Users · NPS · Feature Requests · Pain Points
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Date | User ID | Source | NPS Score | Category | Feedback Summary | Feature Request | Priority | Status | Owner | Action Taken
2025-08-01 | U-001 | Beta App | 9 | UX | Onboarding is smooth, love the design | Add dark mode | Medium | In Backlog | Product | Added to backlog
2025-08-01 | U-002 | Beta App | 7 | Feature | Good but need UPI linking ASAP | UPI bank sync | High | In Sprint 4 | PM | Added to S4
2025-08-02 | U-003 | Feedback Form | 6 | AI | AI suggestions are too generic | More personalized AI | High | Backlog | AI Lead | Prompt improvement planned
2025-08-02 | U-004 | Beta App | 8 | Performance | App is fast, no crashes |  | Low | No Action
2025-08-03 | U-005 | Interview | 5 | Feature | No Hindi support — dealbreaker for parents | Hindi UI | Critical | Sprint 4 | Eng Lead | Added to multilingual sprint
2025-08-03 | U-006 | Beta App | 9 | Feature | Love financial health score concept | Investment breakdown | Medium | Backlog | PM
2025-08-04 | U-007 | NPS Survey | 4 | Bug | Expense categories are confusing | Better categories | High | Sprint 2 | Mobile Dev | Fixed in S2
2025-08-04 | U-008 | Beta App | 8 | AI | The budget advisor saved me ₹3000! | Spending alerts | High | Sprint 2 | Backend Dev | FCM alerts added
2025-08-05 | U-009 | Interview | 7 | Privacy | Worried about data security | Two-factor auth | High | Sprint 3 | Backend Dev | 2FA planned
2025-08-05 | U-010 | Beta App | 9 | General | Best finance app for Indians I've seen | Family sharing | Medium | Sprint 5 | Mobile Dev
NPS SUMMARY
Total Responses | 10
Average NPS Score | 0
Promoters (9-10) | 0
Passives (7-8) | 0
Detractors (0-6) | 0
NPS = Promoters% - Detractors% | 0%

## 21_War_Room
PavelBodle ¦ Launch War Room
MVP Launch Operations · Deployment Checklist · Incident Tracker · Go-Live
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
PRE-LAUNCH CRITICAL CHECKLIST
# | Task | Category | Owner | Status | Target Date | Done Date | Blocker | Priority | Notes
1 | All critical bugs resolved | QA | QA Lead | In Progress | 2025-09-18 |  | 3 bugs open | Critical | P0 must fix
2 | Security penetration test | Security | DevOps Lead | Planned | 2025-09-15 |  |  | Critical | CERT-In compliant
3 | Load test — 1000 concurrent users | Performance | DevOps Lead | Planned | 2025-09-16 |  |  | Critical | k6 test suite
4 | App Store submission (iOS) | Mobile | Mobile Dev | Planned | 2025-09-17 |  | Apple review 2-3d | Critical
5 | Google Play submission | Mobile | Mobile Dev | Planned | 2025-09-17 |  |  | Critical | 24hr review
6 | Privacy policy live on website | Legal | Legal Lead | Done | 2025-07-25 | 2025-07-25 |  | High
7 | Production DB backup verified | DevOps | DevOps Lead | Planned | 2025-09-18 |  |  | High | Test restore process
8 | CDN and WAF configured | DevOps | DevOps Lead | In Progress | 2025-09-10 |  |  | High | Cloudflare
9 | Email transactional setup (SendGrid) | Backend | Backend Dev | Done | 2025-08-01 | 2025-08-01 |  | High
10 | Analytics tracking verified (all events) | Product | PM | Planned | 2025-09-18 |  |  | High | Mixpanel + GA4
11 | Customer support channel ready | Operations | Ops Lead | In Progress | 2025-09-15 |  |  | High | Freshdesk + WhatsApp
12 | Monitoring alerts configured | DevOps | DevOps Lead | In Progress | 2025-09-12 |  |  | High | DataDog + Sentry
13 | Rollback plan documented | Engineering | Eng Lead | Planned | 2025-09-14 |  |  | High | GitHub + Railway
14 | Launch press release ready | Marketing | CMO | In Progress | 2025-09-18 |  |  | Medium | YourStory + MediaNama
15 | Influencer posts scheduled | Marketing | CMO | Planned | 2025-09-20 |  |  | Medium | D-day posts
INCIDENT TRACKER
Incident ID | Title | Severity | Reported By | Time Reported | Time Resolved | Duration | Root Cause | Resolution | Status | Owner | Post-Mortem
INC-001 | DB connection pool exhausted | Critical | DevOps Alert | 2025-08-15 14:22 | 2025-08-15 14:48 | 26 mins | Max connections set too low | Increased pool to 100 | Resolved | DevOps Lead | Yes
INC-002 | OTP SMS delivery failure (Jio) | High | User Report | 2025-08-18 10:05 | 2025-08-18 11:30 | 85 mins | Twilio Jio routing issue | Switched to MSG91 | Resolved | Backend Dev | Yes
INC-003 | AI latency spike > 5s | Medium | Monitoring | 2025-08-20 16:00 | 2025-08-20 16:30 | 30 mins | Groq API rate limit | Added retry + fallback | Resolved | AI Lead | No

## 22_KPI_Dashboard
PavelBodle ¦ KPI Dashboard
North-Star Metrics · Growth · Finance · AI · Product — Investor-Ready
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
GROWTH METRICS
Metric | Target (Monthly) | Current Month | Last Month | MoM Change | MoM % | YTD | Status
DAU (Daily Active Users) | 500 | 387 | 310 |  |  |  | On Track
MAU (Monthly Active Users) | 2000 | 1240 | 850 |  |  |  | On Track
App Downloads (cumulative) | 5000 | 3200 | 2100 |  |  |  | On Track
New Signups (monthly) | 800 | 620 | 410 |  |  |  | On Track
DAU/MAU Ratio | 25% | 0.3121 |  |  |  |  | Watch
7-Day Retention | 40% | 34% | 30% |  |  |  | Watch
30-Day Retention | 20% | 18% | 15% |  |  |  | On Track
NPS Score | 50 | 42 | 38 |  |  |  | Watch
FINANCIAL METRICS
Metric | Target | Current | Last Period |  |  | Annual | Status
MRR (Monthly Recurring Revenue ₹) | 100000 | 38000 | 18000 |  |  |  | On Track
ARR (Annual Run Rate ₹) | 1200000 | 456000 | 216000 |  |  |  | On Track
Monthly Burn Rate (₹) | 800000 | 720000 | 690000 |  |  |  | On Track
Runway (months) | 18 | 14 | 15 |  |  |  | Watch
CAC (₹ per customer) | 500 | 480 | 530 |  |  |  | Good
LTV (12mo, ₹) | 2000 | 1680 | 1200 |  |  |  | On Track
LTV:CAC Ratio | 3x | 3.5 |  |  |  |  | On Track
Gross Margin | 70% | 68% | 65% |  |  |  | On Track
AI PRODUCT METRICS
Metric | Target | Current | Last Week |  |  | Trend | Status
AI Model Accuracy | 90% | 87% | 85% |  |  | ↑ | On Track
Avg AI Latency (ms) | <500 | 420 | 480 |  |  | ↓ Good | Good
AI Cost per Request (₹) | 0.05 | 0.04 | 0.06 |  |  | ↓ Good | Good
Hallucination Rate | <2% | 3.2% | 4.1% |  |  | ↓ | At Risk
AI Feature Adoption | 50% | 38% | 22% |  |  | ↑ | On Track
Prompt Eval Pass Rate | 85% | 82% | 78% |  |  | ↑ | On Track
User Satisfaction (AI) | 4.5/5 | 4.1 | 3.9 |  |  | ↑ | On Track
ENGAGEMENT METRICS
Metric | Target | Current | Benchmark |  |  | Industry Avg | Status
Avg Session Duration (min) | 8 | 6.2 | 5.8 |  |  | 5 min | Good
Sessions per DAU | 2.5 | 2.1 | 1.9 |  |  | 2.0 | Good
Feature Adoption (Budget) | 60% | 42% | 30% |  |  | 50% | Watch
Churn Rate (monthly) | <3% | 4.2% | 5.1% |  |  | 5% | At Risk
App Store Rating | 4.5 | 4.2 | 4.0 |  |  | 4.3 | Watch
Support Ticket Volume | <100/mo | 67 | 82 |  |  |  | Good
Push Notification CTR | 15% | 12% | 10% |  |  | 8% | Good

## 23_Risk
Risk Register
Risk Identification · Impact Analysis · Mitigation · Monitoring
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation Strategy | Contingency | Owner | Status | Review Date | Notes
R-001 | RBI regulatory action on AI financial advice | Regulatory | High | Critical | 12 | Engage RBI consultant, stay as tool not advisor | Pivot product positioning | Founder | Open | 2025-09-01 | Most critical risk
R-002 | Data breach / user financial data leak | Security | Low | Critical | 4 | Encryption at rest+transit, pentest, bug bounty | Incident response plan | DevOps Lead | Mitigating | 2025-08-15 | DPDP Act liability
R-003 | Key engineer departure before MVP | HR | Medium | High | 6 | ESOPs, competitive salary, documentation | Hire contractor backup | Founder | Open | 2025-08-01 | 2 engineers critical path
R-004 | Fundraising falls through | Finance | Medium | High | 6 | Parallel angel outreach, revenue first | Extend runway, cut non-essentials | Founder | Mitigating | 2025-08-15 | 18mo runway needed
R-005 | LLM API cost overrun (10x) | Technical | Medium | Medium | 4 | Rate limiting, caching, model optimization | Switch to cheaper open-source model | AI Lead | Open | 2025-09-01 | Monitor weekly
R-006 | Low user retention / poor PMF | Product | Medium | High | 6 | Weekly user interviews, rapid iteration | Pivot feature set based on data | PM | Open | Ongoing | Track cohort retention
R-007 | App Store rejection | Mobile | Low | High | 3 | Review guidelines early, legal review | Prioritize web app | Mobile Dev | Open | 2025-09-10 | Apple strict on fintech
R-008 | UPI integration delays | Technical | High | Medium | 6 | Start RBI sandbox process early | Manual bank statement import | Backend Dev | Mitigating | 2025-08-20 | Critical feature
R-009 | Competitor launches similar product | Market | Medium | Medium | 4 | Move fast, build moat in AI quality | Double down on India-specific AI | Founder | Monitor | Ongoing | CRED, FI.Money watching
R-010 | Founder burnout / co-founder conflict | Organizational | Low | High | 3 | Clear roles, therapy, vacation policy | Board intervention, equity restructure | Founder | Open | Quarterly | Track founder health

## 24_Meetings
Meeting Notes & Action Items
All Hands · Investor · Sprint · 1:1 · Board
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Date | Meeting Title | Type | Attendees | Agenda | Key Decisions | Action Items | Owner | Due Date | Status
2025-07-07 | Sprint 0 Kickoff | All Hands | All Team | Architecture review, tooling decisions, sprint planning | Chose Turborepo + FastAPI + Expo | Set up repos, legal initiation | Eng Lead | 2025-07-14 | Done
2025-07-14 | Sprint 0 Retro / Sprint 1 Planning | Sprint | Eng Team | Review S0, plan S1 backlog | Carried 2 tasks to S1, added OTP spike | Sprint board updated | Eng Lead | 2025-07-15 | Done
2025-07-18 | Investor Intro — Anand Lunia | Investor | Founder, Anand | Pitch deck walkthrough, vision | Interested, wants traction update in 6wks | Send updated deck with India TAM slide | Founder | 2025-07-22 | Done
2025-07-21 | Legal Setup Review | Legal | Founder, CS Firm | Incorporation status, DPIIT, PAN/TAN | MCA done, DPIIT in process | File GST by July 31 | CFO | 2025-07-31 | In Progress
2025-07-25 | Design Review — Sprint 1 Screens | Product | Founder, Designer, PM | Review Figma for onboarding + expense screens | Minor UX changes approved | Update Figma + handoff to dev | Designer | 2025-07-27 | Done
2025-08-01 | Sprint 1 Mid-Sprint Check | Sprint | Eng Team | Velocity check, blockers | OTP integration blocked — SMS gateway delay | Evaluate MSG91 as alternative | Backend Dev | 2025-08-03 | Done
2025-08-05 | AI Strategy Session | Product | Founder, AI Lead, PM | AI feature prioritization, model choices | Groq for speed, Gemini Flash for quality | Update AI/ML tracker with decisions | AI Lead | 2025-08-07 | Done
2025-08-10 | Marketing Strategy | GTM | Founder, CMO | GTM plan, channel strategy, launch date | Set Oct 1 soft launch target | Finalize content calendar, hire influencer | CMO | 2025-08-17 | In Progress

## 25_Decisions
Decision Log
Key Decisions · Context · Alternatives · Rationale · Reversibility
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Date | Decision | Category | Context | Options Considered | Decision Made | Rationale | Owner | Reversible?
2025-07-03 | Mobile framework choice | Engineering | Native vs cross-platform | Flutter, React Native, Native | React Native (Expo) | Faster dev, JS ecosystem, Expo managed workflow | Eng Lead | Yes — expensive
2025-07-03 | Backend language | Engineering | Scalability vs speed | Django, FastAPI, Node.js | FastAPI (Python) | Best for AI integration, async support, fast | Backend Lead | Costly
2025-07-03 | Primary LLM provider | AI/ML | Cost, latency, quality | OpenAI, Groq, Gemini, Together AI | Groq + Gemini Flash | Groq = speed, Gemini Flash = quality+vision, both free tiers | AI Lead | Easy
2025-07-05 | Vector DB choice | AI/ML | Local vs managed | Pinecone, Weaviate, ChromaDB, FAISS | ChromaDB (local) → Supabase pgvector | ChromaDB free for MVP, pgvector for scale | AI Lead | Medium
2025-07-07 | Cloud deployment | DevOps | Cost, simplicity | AWS, GCP, Railway, Render | Railway (API) + Vercel (Web) | Free tiers sufficient for MVP, zero DevOps overhead | DevOps Lead | Easy
2025-07-10 | Monetization model | Product | Revenue strategy | Ads, Freemium, One-time, B2B | Freemium (Free/Plus/Pro/Family) | Proven in fintech (Mint, YNAB), recurring revenue | Founder | Medium
2025-07-12 | Company structure | Legal | India vs Singapore | Pvt Ltd India, Singapore HoldCo | India Pvt Ltd first | Faster, cheaper, India-first product | Founder | Costly
2025-07-15 | Database choice | Engineering | Relational vs NoSQL | MongoDB, DynamoDB, PostgreSQL | PostgreSQL (Supabase) | ACID compliance critical for finance, free tier | Backend Lead | Costly
2025-07-20 | Analytics provider | Product | Cost + features | Mixpanel, Amplitude, Firebase | Mixpanel (free) + GA4 | Best event tracking for mobile+web, free tier | PM | Easy

## 26_SOPs
SOP Repository
Standard Operating Procedures · Process Library · Version Control
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
SOP ID | Title | Category | Owner | Version | Last Updated | Status | Doc Link | Description
SOP-001 | Engineering Deployment Process | Engineering | DevOps Lead | v1.2 | 2025-07-20 | Active | notion.so/sop1 | Step-by-step Railway deploy + rollback procedure
SOP-002 | Sprint Ceremony Runbook | Engineering | Eng Lead | v1.0 | 2025-07-14 | Active | notion.so/sop2 | Planning, standup, review, retro agenda templates
SOP-003 | AI Prompt Review Process | AI/ML | AI Lead | v1.1 | 2025-07-22 | Active | notion.so/sop3 | How to write, test, version, and retire prompts
SOP-004 | Investor Outreach Process | Fundraising | Founder | v1.0 | 2025-07-18 | Active | notion.so/sop4 | Research → warm intro → deck send → follow-up sequence
SOP-005 | Hiring Process (End-to-End) | HR | HR | v1.0 | 2025-07-16 | Active | notion.so/sop5 | JD → sourcing → screening → interview → offer process
SOP-006 | Customer Support Escalation | Operations | Ops Lead | v1.0 | 2025-08-01 | Active | notion.so/sop6 | L1 → L2 → L3 escalation, SLA definitions
SOP-007 | Security Incident Response | Security | DevOps Lead | v1.0 | 2025-07-30 | Active | notion.so/sop7 | Detection → triage → containment → post-mortem
SOP-008 | Content Creation + Publishing | Marketing | Content Lead | v1.0 | 2025-08-01 | Active | notion.so/sop8 | Brief → draft → review → publish → distribute
SOP-009 | Legal Document Review | Legal | Legal Lead | v1.0 | 2025-07-25 | Active | notion.so/sop9 | Any legal doc must be reviewed by lawyer before signing
SOP-010 | Monthly Financial Close | Finance | CFO | v1.0 | 2025-08-01 | Active | notion.so/sop10 | Month-end books close, burn update, board report

## 27_Competitors
Competitive Analysis
India Fintech Landscape · Feature Matrix · Positioning
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Competitor | Type | Target Segment | Key Features | AI Features | UPI Integration | Pricing | MAU (est) | Funding | Weakness | Our Advantage | Threat Level
CRED | Fintech App | Premium Credit Card users | Bill pay, rewards, CREDcoin | Basic insights | Yes | Free | 25M | $800M | Credit card only, not budgeting | Family + budgeting + AI depth | High
Fi.Money | Neobank | Salaried millennials | Savings account, spends, goals | Smart FIT cards | Yes | Free | 3M | $100M | Neo-bank model, not full finance | Pure AI advisor + no banking lock-in | High
Walnut | Finance App | Budget-conscious users | Expense tracking, budgets | None | No | Free/Premium | 2M | $10M | Dated UI, no AI | Modern AI-first UX + family features | Medium
Money View | Finance App | Credit + savings | Credit score, loans, savings | Basic | Partial | Free | 10M | $250M | Lending focused, not holistic | Full holistic AI advisor | Medium
ET Money | Investment App | Investors | Mutual funds, NPS, insurance | Basic | Yes | Free | 5M | $30M | Investment only, not budgeting | All-in-one budget + invest + AI | Medium
Paytm Money | Investment App | Mass market | Stocks, MF, gold | Basic | Yes | Free | 8M | Part of Paytm | Paytm brand issues, complex UX | Simple + trustworthy AI advisor | Medium
Groww | Investment App | Young investors | Stocks, MF, ETF | Basic | Yes | Free | 15M | $3B | No budgeting, no AI insights | AI + budgeting + investing combined | High
Spendee | Global Finance App | Expats, tech users | Multi-currency tracking | None | No | Free/Premium | 500K | Bootstrapped | Not India-first, no UPI | India-first + UPI + Hindi | Low

## 28_User_Research
User Research
Personas · Interviews · Pain Points · Jobs-to-Be-Done
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
USER PERSONAS
Persona | Age | Occupation | City Tier | Income (₹/mo) | Pain Points | Goals | Tech Savviness | Key Feature Need | Quote
Priya — The Salaried Professional | 28 | Software Engineer | Tier 1 (Bangalore) | 80,000 | Overspending on food/Zomato, no savings habit | Save ₹20k/mo, invest in MF | High | AI expense coach, budget alerts | I know I overspend but I never know WHERE
Ramesh — The Family CFO | 42 | Mid-level Manager | Tier 2 (Pune) | 120,000 | No visibility into family spending, kids education cost | Plan for children's education + retirement | Medium | Family finance hub, goal planner | My wife and I have no idea where our money goes
Sneha — The New Earner | 23 | Fresher / Junior Dev | Tier 1 (Hyderabad) | 35,000 | No financial knowledge, EMI traps | Learn to manage money, build emergency fund | High | Financial health score, education | I just started earning — I don't know what to do
Vikram — The Business Owner | 38 | SME Owner | Tier 2 (Ahmedabad) | 300,000 | Mix of personal and business expenses | Separate personal finance, tax planning | Medium | Expense categorization, tax insights | My CA tells me I have bad personal finance habits
Meena — Regional Language User | 35 | Homemaker | Tier 3 (Madurai) | 45,000 (HH) | English-only apps don't work, husband manages all money | Understand family finances, save for gold | Low | Hindi/Tamil UI, voice assistant | I want to understand our money but I can't read English
USER INTERVIEW LOG
Interview # | Date | Persona Match | Method | Top Pain Point | Top Feature Request | WTP (₹/mo) | Would Recommend? | NPS (0-10) | Key Insight
INT-001 | 2025-07-20 | Salaried Professional | Video Call (Zoom) | Can't track UPI spends automatically | Auto UPI sync | 199 | Yes | 8 | Pain is real — people check bank statements monthly
INT-002 | 2025-07-21 | Family CFO | In-person | Family members spend without visibility | Shared family dashboard | 299 | Yes | 9 | Huge TAM in family finance management
INT-003 | 2025-07-22 | New Earner | WhatsApp Video | Don't know what to invest in | AI that tells me what to do | 149 | Yes | 7 | Need hand-holding, not just data
INT-004 | 2025-07-23 | New Earner | Video Call | Too many apps for different things | All-in-one app | 199 | Yes | 8 | Consolidation is the killer value prop
INT-005 | 2025-07-24 | Regional User | In-person (Pune) | English UI doesn't work for family members | Hindi voice assistant | 99 | Unsure | 6 | Regional language is a massive differentiator
INT-006 | 2025-07-25 | Business Owner | Video Call | Personal vs business expenses mixed | Smart expense tagging | 499 | Yes | 9 | Pro tier opportunity — business-linked finance

## 29_Growth_Exp
Growth Experiments
A/B Tests · Viral Loops · Referral · Retention Experiments
© PavelBodle Startup OS ¦ India AI Fintech ¦ v1.0 ¦ 2026-05-10
Exp ID | Hypothesis | Metric | Control | Variant | Sample Size | Duration | Result | Winner | Impact | Status | Next Action
EXP-001 | Adding progress bar to onboarding will increase completion rate | Onboarding completion % | 68% | 81% | 500 users | 7 days | Variant won +13pp | Variant | High | Shipped | Shipped to 100% users
EXP-002 | WhatsApp reminder for inactive users will improve D7 retention | D7 retention | 22% | 31% | 300 users | 14 days | Variant won +9pp | Variant | High | Shipped | Added to FCM flow
EXP-003 | Showing financial health score on home screen vs buried in profile | DAU engagement | 2.1 sessions | 2.8 sessions | 600 users | 7 days | Variant won +0.7 sessions | Variant | Medium | Shipped | Moved health score to home
EXP-004 | Referral reward ₹50 vs ₹100 cashback | Referral conversion rate | 4.2% | 7.8% | 400 users | 14 days | ₹100 wins but unit econ poor | Control | Low | Learning | Test ₹75 next
EXP-005 | Personalized onboarding (ask goals first) vs generic | Activation rate (adds 1st expense) | 38% | 52% | 500 users | 7 days | Variant won +14pp | Variant | High | Shipped | Goal-first onboarding live
EXP-006 | AI suggestion card on budget overspend | Budget adherence next week | baseline | running | 1000 users | 21 days | In Progress | TBD | TBD | Running | Check at D21
EXP-007 | Hindi push notification vs English for Tier 2 users | CTR on notifications | 9% | running | 300 users | 14 days | In Progress | TBD | TBD | Running | Segmented by phone language
EXP-008 | Social proof on upgrade screen (X users upgraded this week) | Upgrade CVR | 1.8% | planned |  | 7 days | Planned | TBD | TBD | Planned | FOMO + social proof test
EXPERIMENT METRICS
Total Experiments Run | 8
Win Rate | 80%
Currently Running | 2
Shipped to Production | 4